## Detail1 (hidden)
Details for Sum of PV
Activity Name | BL Project Start | BL Project Finish | Actual Start | Actual Finish | Resources | % Work Complete | Labour Rate (per hour) | Material Cost | Utilization (%) | Baseline Duration (Days) | Actual Duration (Days) | PC | AC | PV | EV | CPI | SPI | CV | SV | EAC | PV_Month
MS-9000 Project Kickoff | 2024-09-25 08:00 |  | 2024-09-25 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-09-30
PM-1000 Notice to Proceed | 2024-09-25 08:00 |  |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-09-30
PM-1010 Controls Setup | 2024-09-25 08:00 | 2024-10-04 17:00 | 2024-09-25 08:00 | 2024-10-04 17:00 | PM - Project Controls Lead | 1 | 140 |  | 1 | 9.375 | 9.375 | 10500 | 10500 | 10500 | 10500 | 1 | 1 | 0 | 0 | 10500 | 2024-10-31
PM-1020 Baseline Schedule Build | 2024-10-07 08:00 | 2024-10-22 17:00 | 2024-10-07 08:00 | 2024-10-22 17:00 | PM - Scheduler | 1 | 120 |  | 1 | 15.375 | 15.375 | 14760 | 14760 | 14760 | 14760 | 1 | 1 | 0 | 0 | 14760 | 2024-10-31
PM-1030 Baseline Cost Load | 2024-10-07 08:00 | 2024-10-11 17:00 | 2024-10-07 08:00 | 2024-10-11 17:00 | PM - Cost Controller | 1 | 120 |  | 1 | 4.375 | 4.375 | 4200 | 4200 | 4200 | 4200 | 1 | 1 | 0 | 0 | 4200 | 2024-10-31
PM-1040 Baseline Approval | 2024-10-23 08:00 | 2024-10-24 17:00 | 2024-10-23 08:00 | 2024-10-24 17:00 | PM - Project Manager | 1 | 150 |  | 1 | 1.375 | 1.375 | 1650 | 1650 | 1650 | 1650 | 1 | 1 | 0 | 0 | 1650 | 2024-10-31
PM-1060 Change Control Setup | 2024-10-07 08:00 | 2024-10-16 17:00 | 2024-10-07 08:00 | 2024-10-16 17:00 | PM - Project Controls Lead | 1 | 140 |  | 1 | 9.375 | 9.375 | 10500 | 10500 | 10500 | 10500 | 1 | 1 | 0 | 0 | 10500 | 2024-10-31
PM-1070 Risk Register Setup | 2024-10-07 08:00 | 2024-10-09 17:00 | 2024-10-07 08:00 | 2024-10-09 17:00 | PM - Project Controls Lead | 1 | 140 |  | 1 | 2.375 | 2.375 | 2660 | 2660 | 2660 | 2660 | 1 | 1 | 0 | 0 | 2660 | 2024-10-31
PM-1080 Progress Measurement Plan | 2024-10-07 08:00 | 2024-10-09 17:00 | 2024-10-07 08:00 | 2024-10-09 17:00 | PM - Project Controls Lead | 1 | 140 |  | 1 | 2.375 | 2.375 | 2660 | 2660 | 2660 | 2660 | 1 | 1 | 0 | 0 | 2660 | 2024-10-31
ENG-1100 Engineering Kickoff | 2024-09-26 08:00 | 2024-10-07 17:00 | 2024-09-26 08:00 | 2024-10-07 17:00 | ENG - Engineering Manager | 1 | 145 |  | 1 | 11.375 | 11.375 | 13195 | 13195 | 13195 | 13195 | 1 | 1 | 0 | 0 | 13195 | 2024-10-31
ENG-1110 Finalize Basis of Design | 2024-10-07 08:00 | 2024-10-17 17:00 | 2024-10-07 08:00 | 2024-10-17 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 10.375 | 10.375 | 11205 | 11205 | 11205 | 11205 | 1 | 1 | 0 | 0 | 11205 | 2024-10-31
ENG-1120 Design Criteria | 2024-10-18 08:00 | 2024-10-29 17:00 | 2024-10-18 08:00 | 2024-10-29 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 12285 | 12285 | 1 | 1 | 0 | 0 | 12285 | 2024-10-31
ENG-1130 Model Setup | 2024-10-07 08:00 | 2024-10-16 17:00 | 2024-10-07 08:00 | 2024-10-16 17:00 | ENG - CAD/Designer | 1 | 85 |  | 1 | 9.375 | 9.375 | 6375 | 6375 | 6375 | 6375 | 1 | 1 | 0 | 0 | 6375 | 2024-10-31
ENG-1500 Site Survey | 2024-10-07 08:00 | 2024-10-15 17:00 | 2024-10-07 08:00 | 2024-10-15 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 8.375 | 8.375 | 9045 | 9045 | 9045 | 9045 | 1 | 1 | 0 | 0 | 9045 | 2024-10-31
ENG-1510 Geotech Review | 2024-10-16 08:00 | 2024-10-22 17:00 | 2024-10-16 08:00 | 2024-10-22 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 6.375 | 6.375 | 6885 | 6885 | 6885 | 6885 | 1 | 1 | 0 | 0 | 6885 | 2024-10-31
ENG-1800 Route Selection | 2024-10-07 08:00 | 2024-10-21 17:00 | 2024-10-07 08:00 | 2024-10-21 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2024-10-31
REG-2000 Permit Strategy | 2024-09-25 08:00 | 2024-10-07 17:00 | 2024-09-25 08:00 | 2024-10-07 17:00 | REG - Permitting Lead | 1 | 115 |  | 1 | 12.375 | 12.375 | 11385 | 11385 | 11385 | 11385 | 1 | 1 | 0 | 0 | 11385 | 2024-10-31
ENG-1200 PFD Development | 2024-10-18 08:00 | 2024-11-05 17:00 | 2024-10-18 08:00 | 2024-11-05 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 18.375 | 18.375 | 19845 | 19845 | 19845 | 19845 | 1 | 1 | 0 | 0 | 19845 | 2024-11-30
ENG-1210 Heat& Material Balance | 2024-11-08 08:00 | 2024-11-21 17:00 | 2024-11-08 08:00 | 2024-11-21 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2024-11-30
ENG-1520 Grading Plan | 2024-10-23 08:00 | 2024-11-08 17:00 | 2024-10-23 08:00 | 2024-11-08 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2024-11-30
ENG-1530 Foundations Design | 2024-10-23 08:00 | 2024-11-19 17:00 | 2024-10-23 08:00 | 2024-11-19 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 27.375 | 27.375 | 29565 | 29565 | 29565 | 29565 | 1 | 1 | 0 | 0 | 29565 | 2024-11-30
ENG-1640 Grounding Design | 2024-11-11 08:00 | 2024-11-25 17:00 | 2024-11-11 08:00 | 2024-11-25 17:00 | ENG - Electrical Engineer | 1 | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2024-11-30
ENG-1810 Environmental Screening | 2024-10-22 08:00 | 2024-11-12 17:00 | 2024-10-22 08:00 | 2024-11-12 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2024-11-30
ENG-1840 Wall Thickness Calc | 2024-10-22 08:00 | 2024-11-08 17:00 | 2024-10-22 08:00 | 2024-11-08 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 17.375 | 17.375 | 18765 | 18765 | 18765 | 18765 | 1 | 1 | 0 | 0 | 18765 | 2024-11-30
PRO-3140 Steel Fabrication | 2024-09-25 08:00 | 2024-11-08 17:00 | 2024-09-25 08:00 | 2024-11-08 17:00 | MAT - Structural Steel Supply | 1 |  | 2500000 | 1 | 44.375 | 44.375 | 2500000 | 2500000 | 2500000 | 2500000 | 1 | 1 | 0 | 0 | 2500000 | 2024-11-30
PRO-3150 Deliver Steel | 2024-11-11 08:00 | 2024-11-12 17:00 | 2025-03-14 08:00 | 2025-03-17 17:00 | PROC - Buyer/Expeditor | 1 | 85 |  | 1 | 1.375 | 3.375 | 935 | 2295 | 935 | 935 | 0.40741 | 1 | -1360 | 0 | 2295 | 2024-11-30
PRO-3300 RFQ (Line Pipe) | 2024-11-11 08:00 | 2024-11-27 17:00 | 2024-11-11 08:00 | 2024-11-27 17:00 | PROC - Procurement Lead | 1 | 120 |  | 1 | 16.375 | 16.375 | 15720 | 15720 | 15720 | 15720 | 1 | 1 | 0 | 0 | 15720 | 2024-11-30
PRO-3310 Line Pipe Award | 2024-11-28 08:00 |  | 2024-11-28 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-11-30
ENG-1220 P&ID Development | 2024-11-20 08:00 | 2024-12-26 17:00 | 2024-11-20 08:00 | 2024-12-26 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 36.375 | 36.375 | 39285 | 39285 | 39285 | 39285 | 1 | 1 | 0 | 0 | 39285 | 2024-12-31
ENG-1260 HAZOP Prep | 2024-12-27 08:00 | 2024-12-31 17:00 | 2024-12-27 08:00 | 2024-12-31 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 4.375 | 4.375 | 4725 | 4725 | 4725 | 4725 | 1 | 1 | 0 | 0 | 4725 | 2024-12-31
ENG-1540 Steel Design | 2024-11-20 08:00 | 2024-12-12 17:00 | 2024-11-20 08:00 | 2024-12-12 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 22.375 | 22.375 | 24165 | 24165 | 24165 | 24165 | 1 | 1 | 0 | 0 | 24165 | 2024-12-31
ENG-1560 Steel Connection Details | 2024-12-13 08:00 | 2024-12-26 17:00 | 2024-12-13 08:00 | 2024-12-26 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2024-12-31
ENG-1820 ROW Support | 2024-11-13 08:00 | 2024-12-11 17:00 | 2024-11-13 08:00 | 2024-12-11 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 28.375 | 28.375 | 30645 | 30645 | 30645 | 30645 | 1 | 1 | 0 | 0 | 30645 | 2024-12-31
ENG-1830 Watercourse Design | 2024-11-13 08:00 | 2024-12-05 17:00 | 2024-11-13 08:00 | 2024-12-05 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 22.375 | 22.375 | 24165 | 24165 | 24165 | 24165 | 1 | 1 | 0 | 0 | 24165 | 2024-12-31
REG-2020 Mitigation Plan | 2024-11-13 08:00 | 2024-12-04 17:00 | 2024-11-13 08:00 | 2024-12-04 17:00 | REG - Environmental Specialist | 1 | 105 |  | 1 | 21.375 | 21.375 | 17955 | 17955 | 17955 | 17955 | 1 | 1 | 0 | 0 | 17955 | 2024-12-31
PRO-3100 RFQ (Structural Steel) | 2024-12-13 08:00 | 2024-12-20 17:00 | 2024-12-13 08:00 | 2024-12-20 17:00 | PROC - Procurement Lead | 1 | 120 |  | 1 | 7.375 | 7.375 | 7080 | 7080 | 7080 | 7080 | 1 | 1 | 0 | 0 | 7080 | 2024-12-31
PRO-3110 Steel Award | 2024-12-23 08:00 |  | 2024-12-23 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-12-31
PRO-3315 Line Pipe Mill Data / Coating Submittals | 2024-11-28 08:00 | 2024-12-26 17:00 | 2024-11-28 08:00 | 2024-12-26 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 28.375 | 28.375 | 30645 | 30645 | 30645 | 30645 | 1 | 1 | 0 | 0 | 30645 | 2024-12-31
PRO-3340 Receive Pipeline Valves | 2024-11-28 08:00 | 2024-12-20 17:00 | 2024-11-28 08:00 | 2024-12-20 17:00 | PROC - Buyer/Expeditor | 1 | 85 |  | 1 | 22.375 | 22.375 | 15215 | 15215 | 15215 | 15215 | 1 | 1 | 0 | 0 | 15215 | 2024-12-31
ENG-1230 Control Philosophy | 2024-12-30 08:00 | 2025-01-10 17:00 | 2024-12-30 08:00 | 2025-01-10 17:00 | ENG - Instrument/Controls Engineer | 1 | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 12285 | 12285 | 1 | 1 | 0 | 0 | 12285 | 2025-01-31
ENG-1240 Relief Review | 2024-12-27 08:00 | 2025-01-02 17:00 | 2024-12-27 08:00 | 2025-01-02 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 6.375 | 6.375 | 6885 | 6885 | 6885 | 6885 | 1 | 1 | 0 | 0 | 6885 | 2025-01-31
ENG-1250 Cause& Effect Draft | 2025-01-10 08:00 | 2025-01-27 17:00 | 2025-01-10 08:00 | 2025-01-27 17:00 | ENG - Instrument/Controls Engineer | 1 | 135 |  | 1 | 17.375 | 17.375 | 18765 | 18765 | 18765 | 18765 | 1 | 1 | 0 | 0 | 18765 | 2025-01-31
ENG-1270 HAZOP Session | 2024-12-31 08:00 | 2025-01-09 17:00 | 2024-12-31 08:00 | 2025-01-09 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 9.375 | 9.375 | 10125 | 10125 | 10125 | 10125 | 1 | 1 | 0 | 0 | 10125 | 2025-01-31
ENG-1280 HAZOP Closeout | 2025-01-10 08:00 | 2025-01-28 17:00 | 2025-01-10 08:00 | 2025-01-28 17:00 | ENG - Process Engineer | 1 | 135 |  | 1 | 18.375 | 18.375 | 19845 | 19845 | 19845 | 19845 | 1 | 1 | 0 | 0 | 19845 | 2025-01-31
ENG-1300 Equipment List | 2024-12-27 08:00 | 2025-01-14 17:00 | 2024-12-27 08:00 | 2025-01-14 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 18.375 | 18.375 | 19845 | 19845 | 19845 | 19845 | 1 | 1 | 0 | 0 | 19845 | 2025-01-31
ENG-1310 Compressor Datasheets | 2025-01-15 08:00 | 2025-01-29 17:00 | 2025-01-15 08:00 | 2025-01-29 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2025-01-31
ENG-1320 Separator Datasheets | 2025-01-15 08:00 | 2025-01-29 17:00 | 2025-01-15 08:00 | 2025-01-29 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2025-01-31
ENG-1330 Dehydration Datasheets | 2025-01-15 08:00 | 2025-01-28 17:00 | 2025-01-15 08:00 | 2025-01-28 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2025-01-31
ENG-1340 Cooler Datasheets | 2025-01-15 08:00 | 2025-01-28 17:00 | 2025-01-15 08:00 | 2025-01-28 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2025-01-31
ENG-1350 Valve List | 2025-01-22 08:00 | 2025-01-29 17:00 | 2025-01-22 08:00 | 2025-01-29 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 7.375 | 7.375 | 7965 | 7965 | 7965 | 7965 | 1 | 1 | 0 | 0 | 7965 | 2025-01-31
ENG-1360 Line List | 2024-12-27 08:00 | 2025-01-21 17:00 | 2024-12-27 08:00 | 2025-01-21 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 25.375 | 25.375 | 27405 | 27405 | 27405 | 27405 | 1 | 1 | 0 | 0 | 27405 | 2025-01-31
ENG-1550 Anchor Bolt Plans | 2024-12-13 08:00 | 2025-01-01 17:00 | 2024-12-13 08:00 | 2025-01-01 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 19.375 | 19.375 | 20925 | 20925 | 20925 | 20925 | 1 | 1 | 0 | 0 | 20925 | 2025-01-31
ENG-1570 Structural IFC Issued |  | 2025-01-02 17:00 |  | 2025-01-02 17:00 |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-01-31
ENG-1650 Area Classification | 2024-12-27 08:00 | 2025-01-08 17:00 | 2024-12-27 08:00 | 2025-01-08 17:00 | ENG - Electrical Engineer | 1 | 135 |  | 1 | 12.375 | 12.375 | 13365 | 13365 | 13365 | 13365 | 1 | 1 | 0 | 0 | 13365 | 2025-01-31
ENG-1700 Instrument Index | 2024-12-27 08:00 | 2025-01-17 17:00 | 2024-12-27 08:00 | 2025-01-17 17:00 | ENG - Instrument/Controls Engineer | 1 | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2025-01-31
ENG-1730 Control Narrative | 2025-01-10 08:00 | 2025-01-30 17:00 | 2025-01-10 08:00 | 2025-01-30 17:00 | ENG - Instrument/Controls Engineer | 1 | 135 |  | 1 | 20.375 | 20.375 | 22005 | 22005 | 22005 | 22005 | 1 | 1 | 0 | 0 | 22005 | 2025-01-31
ENG-1850 Alignment Sheets Issued | 2024-12-06 08:00 | 2025-01-06 17:00 | 2024-12-06 08:00 | 2025-01-06 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 31.375 | 31.375 | 33885 | 33885 | 33885 | 33885 | 1 | 1 | 0 | 0 | 33885 | 2025-01-31
ENG-1860 Tie-In Details | 2025-01-07 08:00 | 2025-01-30 17:00 | 2025-01-07 08:00 | 2025-01-30 17:00 | ENG - Pipeline Engineer | 1 | 135 |  | 1 | 23.375 | 23.375 | 25245 | 25245 | 25245 | 25245 | 1 | 1 | 0 | 0 | 25245 | 2025-01-31
ENG-1870 Pipeline IFC Issued |  | 2025-01-31 17:00 |  | 2025-01-31 17:00 |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-01-31
PRO-3120 Steel Shop Drawings | 2024-12-23 08:00 | 2025-01-15 17:00 | 2024-12-23 08:00 | 2025-01-15 17:00 | ENG - Civil/Structural Engineer | 1 | 135 |  | 1 | 23.375 | 23.375 | 25245 | 25245 | 25245 | 25245 | 1 | 1 | 0 | 0 | 25245 | 2025-01-31
ENG-1140 30% Design Review | 2025-02-05 08:00 | 2025-02-14 17:00 | 2025-02-05 08:00 | 2025-02-14 17:00 | ENG - Engineering Manager | 1 | 145 |  | 1 | 9.375 | 9.375 | 10875 | 10875 | 10875 | 10875 | 1 | 1 | 0 | 0 | 10875 | 2025-02-28
ENG-1370 Piping Classes | 2025-01-22 08:00 | 2025-02-07 17:00 | 2025-01-22 08:00 | 2025-02-07 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2025-02-28
ENG-1600 Load Study | 2025-01-15 08:00 | 2025-02-04 17:00 | 2025-01-15 08:00 | 2025-02-04 17:00 | ENG - Electrical Engineer | 1 | 135 |  | 1 | 20.375 | 20.375 | 22005 | 22005 | 22005 | 22005 | 1 | 1 | 0 | 0 | 22005 | 2025-02-28
ENG-1610 Single-Line Diagrams | 2025-02-05 08:00 | 2025-02-26 17:00 | 2025-02-05 08:00 | 2025-02-26 17:00 | ENG - Electrical Engineer | 1 | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2025-02-28
ENG-1710 IO List | 2025-01-20 08:00 | 2025-02-05 17:00 | 2025-01-20 08:00 | 2025-02-05 17:00 | ENG - Instrument/Controls Engineer | 1 | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2025-02-28
ENG-1740 Cause& Effect Final | 2025-01-29 08:00 | 2025-02-14 17:00 | 2025-01-29 08:00 | 2025-02-14 17:00 | ENG - Instrument/Controls Engineer | 1 | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2025-02-28
ENG-1750 DCS Architecture | 2025-02-10 08:00 | 2025-02-21 17:00 | 2025-02-10 08:00 | 2025-02-21 17:00 | ENG - Instrument/Controls Engineer | 1 | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 12285 | 12285 | 1 | 1 | 0 | 0 | 12285 | 2025-02-28
REG-2010 Submit Approvals | 2025-01-31 08:00 | 2025-02-19 17:00 | 2025-01-31 08:00 | 2025-02-19 17:00 | REG - Permitting Lead | 1 | 115 |  | 1 | 19.375 | 19.375 | 17825 | 17825 | 17825 | 17825 | 1 | 1 | 0 | 0 | 17825 | 2025-02-28
REG-2030 Land Access Agreements | 2024-12-12 08:00 | 2025-02-10 17:00 | 2024-12-12 08:00 | 2025-02-10 17:00 | REG - Land Agent | 1 | 95 |  | 1 | 60.375 | 60.375 | 45885 | 45885 | 45885 | 45885 | 1 | 1 | 0 | 0 | 45885 | 2025-02-28
REG-2040 Indigenous Engagement | 2024-12-12 08:00 | 2025-02-20 17:00 | 2024-12-12 08:00 | 2025-02-20 17:00 | REG - Permitting Lead | 1 | 115 |  | 1 | 70.375 | 70.375 | 64745 | 64745 | 64745 | 64745 | 1 | 1 | 0 | 0 | 64745 | 2025-02-28
REG-2050 ROW Secured | 2025-02-21 08:00 | 2025-02-24 17:00 | 2025-02-21 08:00 | 2025-02-24 17:00 | REG - Land Agent | 1 | 95 |  | 1 | 3.375 | 3.375 | 2565 | 2565 | 2565 | 2565 | 1 | 1 | 0 | 0 | 2565 | 2025-02-28
REG-2060 Permits Approved | 2025-02-20 08:00 | 2025-02-21 17:00 | 2025-02-20 08:00 | 2025-02-21 17:00 |  | 1 |  |  | 1 | 1.375 | 1.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-02-28
PRO-3000 RFQ (Compressor) | 2025-01-30 08:00 | 2025-02-13 17:00 | 2025-01-30 08:00 | 2025-02-13 17:00 | PROC - Procurement Lead | 1 | 120 |  | 1 | 14.375 | 14.375 | 13800 | 13800 | 13800 | 13800 | 1 | 1 | 0 | 0 | 13800 | 2025-02-28
PRO-3010 Tech Eval (Compressor) | 2025-02-14 08:00 | 2025-02-21 17:00 | 2025-02-14 08:00 | 2025-02-21 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 7.375 | 7.375 | 7965 | 7965 | 7965 | 7965 | 1 | 1 | 0 | 0 | 7965 | 2025-02-28
PRO-3160 RFQ (Piping Bulks) | 2025-02-10 08:00 | 2025-02-18 17:00 | 2025-03-17 08:00 | 2025-03-25 17:00 |  | 1 |  |  | 1 | 8.375 | 8.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-02-28
PRO-3170 Piping Bulks Award | 2025-02-19 08:00 | 2025-02-20 17:00 | 2025-03-25 08:00 | 2025-03-26 17:00 | PROC - Procurement Lead | 1 | 120 |  | 1 | 1.375 | 1.375 | 1320 | 1320 | 1320 | 1320 | 1 | 1 | 0 | 0 | 1320 | 2025-02-28
PRO-3320 Line Pipe Coating | 2024-12-27 08:00 | 2025-02-17 17:00 | 2024-12-27 08:00 | 2025-02-17 17:00 | MAT - Line Pipe Supply | 1 |  | 4500000 | 1 | 52.375 | 52.375 | 4500000 | 4500000 | 4500000 | 4500000 | 1 | 1 | 0 | 0 | 4500000 | 2025-02-28
PRO-3330 Deliver Line Pipe | 2025-02-18 08:00 | 2025-02-24 17:00 | 2025-02-18 08:00 | 2025-02-24 17:00 | PROC - Buyer/Expeditor | 1 | 85 |  | 1 | 6.375 | 6.375 | 4335 | 4335 | 4335 | 4335 | 1 | 1 | 0 | 0 | 4335 | 2025-02-28
ENG-1380 BIM Model 30% | 2025-02-10 08:00 | 2025-03-03 17:00 | 2025-02-10 08:00 | 2025-03-03 17:00 | ENG - CAD/Designer | 1 | 85 |  | 1 | 21.375 | 21.375 | 14535 | 14535 | 14535 | 14535 | 1 | 1 | 0 | 0 | 14535 | 2025-03-31
ENG-1390 BIM Model 60% | 2025-03-04 08:00 | 2025-03-31 17:00 | 2025-03-04 08:00 |  | ENG - CAD/Designer | 0.1 | 85 |  | 1 | 27.375 | 0 | 18615 | 0 | 18615 | 1861.5 |  | 0.1 | 1861.5 | -16753.5 | 16753.5 | 2025-03-31
ENG-1620 MCC Sizing | 2025-02-27 08:00 | 2025-03-12 17:00 | 2025-02-27 08:00 |  | ENG - Electrical Engineer | 0.4 | 135 |  | 1 | 13.375 | 0 | 14445 | 0 | 14445 | 5778 |  | 0.4 | 5778 | -8667 | 8667 | 2025-03-31
ENG-1720 Loop Diagrams | 2025-02-06 08:00 | 2025-03-07 17:00 | 2025-02-06 08:00 |  | ENG - Instrument/Controls Engineer | 0.9091 | 135 |  | 1 | 29.375 | 0 | 31725 | 0 | 31725 | 28841.1975 |  | 0.9091 | 28841.1975 | -2883.8025 | 2883.8025 | 2025-03-31
ENG-1760 Controls IFC Issued |  | 2025-03-10 17:00 |  | 2025-03-11 17:00 |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-03-31
PRO-3020 Comm Eval (Compressor) | 2025-02-24 08:00 | 2025-03-06 17:00 | 2025-02-24 08:00 |  | ENG - Mechanical Engineer | 0.8889 | 135 |  | 1 | 10.375 | 0 | 11205 | 0 | 11205 | 9960.1245 |  | 0.8889 | 9960.1245 | -1244.8755 | 1244.8755 | 2025-03-31
PRO-3030 Compressor PO Award | 2025-03-07 08:00 |  | 2025-03-07 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-03-31
PRO-3030 Compressor Shop Drawings | 2025-03-07 08:00 | 2025-03-26 17:00 | 2025-03-07 08:00 | 2025-04-01 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 19.375 | 25.375 | 20925 | 27405 | 20925 | 20925 | 0.76355 | 1 | -6480 | 0 | 27405 | 2025-03-31
PRO-3180 Receive Piping Bulks | 2025-02-21 08:00 | 2025-03-19 17:00 | 2025-02-21 08:00 |  | PROC - Procurement Lead | 0.4737 | 120 |  | 1 | 26.375 | 0 | 25320 | 0 | 25320 | 11994.084 |  | 0.4737 | 11994.084 | -13325.916 | 13325.916 | 2025-03-31
ENG-1150 60% Design Review | 2025-04-10 08:00 | 2025-04-21 17:00 | 2025-04-10 08:00 | 2025-04-22 08:00 | ENG - Engineering Manager | 1 | 145 |  | 1 | 11.375 | 12 | 13195 | 13920 | 13195 | 13195 | 0.94792 | 1 | -725 | 0 | 13920 | 2025-04-30
ENG-1630 Cable Schedule | 2025-03-13 08:00 | 2025-04-03 17:00 | 2025-03-13 08:00 | 2025-04-03 17:00 | ENG - Electrical Engineer | 1 | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2025-04-30
ENG-1660 Substation Upgrade | 2025-03-13 08:00 | 2025-04-09 17:00 | 2025-03-13 08:00 | 2025-04-10 17:00 | ENG - Electrical Engineer | 1 | 135 |  | 1 | 27.375 | 28.375 | 29565 | 30645 | 29565 | 29565 | 0.96476 | 1 | -1080 | 0 | 30645 | 2025-04-30
ENG-1670 Electrical IFC Issued | 2025-04-10 08:00 |  | 2025-04-10 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-04-30
PRO-3040 Vendor Review Cycle 1 | 2025-03-27 08:00 | 2025-04-08 17:00 | 2025-03-27 08:00 | 2025-04-10 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 12.375 | 14.375 | 13365 | 15525 | 13365 | 13365 | 0.86087 | 1 | -2160 | 0 | 15525 | 2025-04-30
PRO-3050 Vendor Review Cycle 2 | 2025-04-09 08:00 | 2025-04-17 17:00 | 2025-04-10 08:00 | 2025-04-18 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 8.375 | 8.375 | 9045 | 9045 | 9045 | 9045 | 1 | 1 | 0 | 0 | 9045 | 2025-04-30
PRO-3190 RFQ (E&I Bulks) | 2025-04-04 08:00 | 2025-04-10 17:00 | 2025-03-26 08:00 | 2025-04-11 17:00 |  | 1 |  |  | 1 | 6.375 | 16.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-04-30
PRO-3200 E&I Bulks Award | 2025-04-11 08:00 |  | 2025-04-11 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-04-30
ENG-1160 90% Design Review | 2025-05-21 08:00 | 2025-05-30 17:00 | 2025-05-21 | 2025-06-04 08:00 | ENG - Engineering Manager | 1 | 145 |  | 1 | 9.375 | 14.3333 | 10875 | 16626.6667 | 10875 | 10875 | 0.65407 | 1 | -5751.6667 | 0 | 16626.6667 | 2025-05-31
ENG-1400 BIM Model 90% | 2025-04-01 08:00 | 2025-05-01 17:00 | 2025-04-01 08:00 | 2025-05-01 17:00 | ENG - CAD/Designer | 1 | 85 |  | 1 | 30.375 | 30.375 | 20655 | 20655 | 20655 | 20655 | 1 | 1 | 0 | 0 | 20655 | 2025-05-31
ENG-1410 Isometrics Issued | 2025-05-02 08:00 | 2025-05-20 17:00 | 2025-05-02 08:00 | 2025-05-20 17:00 | ENG - CAD/Designer | 1 | 85 |  | 1 | 18.375 | 18.375 | 12495 | 12495 | 12495 | 12495 | 1 | 1 | 0 | 0 | 12495 | 2025-05-31
PRO-3205 Electrical Shop Drawings | 2025-04-11 08:00 | 2025-05-06 17:00 | 2025-04-11 08:00 | 2025-05-06 17:00 | ENG - Electrical Engineer | 1 | 135 |  | 1 | 25.375 | 25.375 | 27405 | 27405 | 27405 | 27405 | 1 | 1 | 0 | 0 | 27405 | 2025-05-31
MS-9010 IFC Issued (All Disciplines) |  | 2025-06-06 17:00 |  | 2025-06-09 17:00 |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
ENG-1420 Pipe Support Design | 2025-05-21 08:00 | 2025-06-05 17:00 | 2025-05-21 08:00 | 2025-06-05 17:00 | ENG - Mechanical Engineer | 1 | 135 |  | 1 | 15.375 | 15.375 | 16605 | 16605 | 16605 | 16605 | 1 | 1 | 0 | 0 | 16605 | 2025-06-30
ENG-1430 Mech Package IFC Issued |  | 2025-06-06 17:00 |  | 2025-06-06 17:00 |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
PRO-3210 Receive E&I Bulks | 2025-05-07 08:00 | 2025-06-19 17:00 | 2025-05-07 08:00 | 2025-06-19 17:00 | PROC - Buyer/Expeditor | 1 | 85 |  | 1 | 43.375 | 43.375 | 29495 | 29495 | 29495 | 29495 | 1 | 1 | 0 | 0 | 29495 | 2025-06-30
PRO-3400 Tender Civil Contractor | 2025-06-06 08:00 | 2025-06-25 17:00 | 2025-06-06 08:00 | 2025-06-25 17:00 | PM - Contracts/Admin | 1 | 85 |  | 1 | 19.375 | 19.375 | 13175 | 13175 | 13175 | 13175 | 1 | 1 | 0 | 0 | 13175 | 2025-06-30
PRO-3410 Civil Contractor Award | 2025-06-26 08:00 |  | 2025-06-26 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
PRO-3440 Tender E&I Contractor | 2025-06-06 08:00 | 2025-06-26 17:00 | 2025-06-06 08:00 | 2025-06-26 17:00 | PM - Contracts/Admin | 1 | 85 |  | 1 | 20.375 | 20.375 | 13855 | 13855 | 13855 | 13855 | 1 | 1 | 0 | 0 | 13855 | 2025-06-30
PRO-3450 E&I Contractor Award | 2025-06-27 08:00 | 2025-06-27 17:00 | 2025-06-27 08:00 |  | PM - Contracts/Admin | 0 | 85 |  | 1 | 0.375 | 0 | 255 | 0 | 255 | 0 |  | 0 | 0 | -255 | 255 | 2025-06-30
PRO-3460 Tender Pipeline Contractor | 2025-06-06 08:00 | 2025-06-24 17:00 | 2025-06-06 08:00 | 2025-06-24 17:00 | PM - Contracts/Admin | 1 | 85 |  | 1 | 18.375 | 18.375 | 12495 | 12495 | 12495 | 12495 | 1 | 1 | 0 | 0 | 12495 | 2025-06-30
PRO-3470 Pipeline Contractor Award | 2025-06-25 08:00 |  | 2025-06-25 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
PRO-3420 Tender Mechanical Contractor | 2025-06-06 08:00 | 2025-07-01 17:00 | 2025-06-06 08:00 | 2025-07-01 17:00 | PM - Contracts/Admin | 1 | 85 |  | 1 | 25.375 | 25.375 | 17255 | 17255 | 17255 | 17255 | 1 | 1 | 0 | 0 | 17255 | 2025-07-31
PRO-3430 Mechanical Contractor Award | 2025-07-02 08:00 |  | 2025-07-02 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-07-31
CON-4000 Plant Mobilization | 2025-06-26 08:00 | 2025-07-10 17:00 | 2025-06-26 08:00 | 2025-07-17 17:00 | CIV - Site Prep Crew | 1 | 120 |  | 1 | 14.375 | 21.375 | 13800 | 20520 | 13800 | 13800 | 0.67251 | 1 | -6720 | 0 | 20520 | 2025-07-31
CON-4010 Temp Facilities Setup | 2025-07-11 08:00 | 2025-07-22 17:00 | 2025-07-11 08:00 | 2025-07-24 17:00 | CIV - Site Prep Crew | 1 | 120 |  | 1 | 11.375 | 13.375 | 10920 | 12840 | 10920 | 10920 | 0.85047 | 1 | -1920 | 0 | 12840 | 2025-07-31
CON-4020 Survey& Layout | 2025-07-11 08:00 | 2025-07-15 17:00 | 2025-07-11 08:00 | 2025-07-18 17:00 | CIV - Site Prep Crew | 1 | 120 |  | 1 | 4.375 | 7.375 | 4200 | 7080 | 4200 | 4200 | 0.59322 | 1 | -2880 | 0 | 7080 | 2025-07-31
CON-4030 Clearing | 2025-07-16 08:00 | 2025-07-22 17:00 | 2025-07-18 08:00 | 2025-07-28 17:00 | CIV - Site Prep Crew | 1 | 120 |  | 1 | 6.375 | 10.375 | 6120 | 9960 | 6120 | 6120 | 0.61446 | 1 | -3840 | 0 | 9960 | 2025-07-31
PL-5000 Pipeline Mobilization | 2025-06-25 08:00 | 2025-07-04 17:00 | 2025-06-25 08:00 | 2025-07-04 | PIPE - Pipeline Superintendent | 1 | 140 |  | 1 | 9.375 | 8.6667 | 10500 | 9706.6667 | 10500 | 10500 | 1.0817 | 1 | 793.3333 | 0 | 9706.6667 | 2025-07-31
PL-5010 Survey& Staking | 2025-07-07 08:00 | 2025-07-15 17:00 | 2025-07-07 08:00 | 2025-07-15 17:00 | PIPE - ROW Clearing Crew | 1 | 125 |  | 1 | 8.375 | 8.375 | 8375 | 8375 | 8375 | 8375 | 1 | 1 | 0 | 0 | 8375 | 2025-07-31
CON-4100 Earthworks | 2025-07-23 08:00 | 2025-08-07 17:00 | 2025-07-28 08:00 | 2025-08-21 17:00 | CIV - Concrete Crew | 1 | 135 |  | 3 | 15.375 | 24.375 | 49815 | 78975 | 49815 | 49815 | 0.63077 | 1 | -29160 | 0 | 78975 | 2025-08-31
CON-4120 Form Foundations | 2025-08-08 08:00 | 2025-08-26 17:00 | 2025-09-19 08:00 | 2025-10-07 17:00 | CIV - Concrete Crew | 1 | 135 |  | 3 | 18.375 | 18.375 | 59535 | 59535 | 59535 | 59535 | 1 | 1 | 0 | 0 | 59535 | 2025-08-31
CON-4500 Install Ground Grid | 2025-08-08 08:00 | 2025-08-18 17:00 | 2025-08-21 08:00 | 2025-08-29 17:00 | E&I - Electrical Crew | 1 | 145 |  | 1 | 10.375 | 8.375 | 12035 | 9715 | 12035 | 12035 | 1.2388 | 1 | 2320 | 0 | 9715 | 2025-08-31
PL-5020 ROW Clearing | 2025-07-16 08:00 | 2025-08-04 17:00 | 2025-07-16 08:00 | 2025-08-04 17:00 | PIPE - ROW Clearing Crew | 1 | 125 |  | 4 | 19.375 | 19.375 | 77500 | 77500 | 77500 | 77500 | 1 | 1 | 0 | 0 | 77500 | 2025-08-31
PL-5030 Access Improvements | 2025-08-05 08:00 | 2025-08-19 17:00 | 2025-08-05 08:00 | 2025-08-19 17:00 | PIPE - ROW Clearing Crew | 1 | 125 |  | 1 | 14.375 | 14.375 | 14375 | 14375 | 14375 | 14375 | 1 | 1 | 0 | 0 | 14375 | 2025-08-31
PRO-3060 Compressor Fabrication | 2025-04-18 08:00 | 2025-09-16 17:00 | 2025-04-18 08:00 | 2025-09-16 17:00 | MAT - Compressor Package | 1 |  | 62000000 | 1 | 151.375 | 151.375 | 62000000 | 62000000 | 62000000 | 62000000 | 1 | 1 | 0 | 0 | 62000000 | 2025-09-30
PRO-3070 Compressor FAT | 2025-09-17 08:00 | 2025-09-18 17:00 | 2025-09-17 08:00 | 2025-09-18 17:00 | PROC - QA/QC Inspector | 1 | 90 |  | 1 | 1.375 | 1.375 | 990 | 990 | 990 | 990 | 1 | 1 | 0 | 0 | 990 | 2025-09-30
PRO-3080 Ship Compressor | 2025-09-19 08:00 | 2025-09-30 17:00 | 2025-09-19 08:00 | 2025-09-30 17:00 | PROC - Buyer/Expeditor | 1 | 85 |  | 1 | 11.375 | 11.375 | 7735 | 7735 | 7735 | 7735 | 1 | 1 | 0 | 0 | 7735 | 2025-09-30
CON-4110 Underground Utilities | 2025-08-08 08:00 | 2025-09-08 17:00 | 2025-08-21 08:00 | 2025-09-19 17:00 | CIV - Concrete Crew | 1 | 135 |  | 3 | 31.375 | 29.375 | 101655 | 95175 | 101655 | 101655 | 1.0681 | 1 | 6480 | 0 | 95175 | 2025-09-30
CON-4130 Rebar Install | 2025-08-27 08:00 | 2025-09-01 17:00 | 2025-10-07 08:00 | 2025-10-17 08:00 | CIV - Concrete Crew | 1 | 135 |  | 4 | 5.375 | 10 | 23220 | 43200 | 23220 | 23220 | 0.5375 | 1 | -19980 | 0 | 43200 | 2025-09-30
PL-5100 Pipe Stringing | 2025-08-20 08:00 | 2025-09-05 17:00 | 2025-08-20 08:00 | 2025-09-05 17:00 | PIPE - Stringing Crew | 1 | 130 |  | 3 | 16.375 | 16.375 | 51090 | 51090 | 51090 | 51090 | 1 | 1 | 0 | 0 | 51090 | 2025-09-30
PL-5110 Pipe Bending | 2025-09-08 08:00 | 2025-09-17 17:00 | 2025-09-08 08:00 | 2025-09-17 17:00 | PIPE - Bending Crew | 1 | 140 |  | 1 | 9.375 | 9.375 | 10500 | 10500 | 10500 | 10500 | 1 | 1 | 0 | 0 | 10500 | 2025-09-30
PL-5200 Watercourse Crossing | 2025-08-20 08:00 | 2025-09-03 17:00 | 2025-08-20 08:00 | 2025-09-03 17:00 | PIPE - ROW Clearing Crew | 1 | 125 |  | 1 | 14.375 | 14.375 | 14375 | 14375 | 14375 | 14375 | 1 | 1 | 0 | 0 | 14375 | 2025-09-30
PL-5210 Road Crossing | 2025-08-20 08:00 | 2025-09-02 17:00 | 2025-08-20 08:00 | 2025-09-02 17:00 | PIPE - ROW Clearing Crew | 1 | 125 |  | 1 | 13.375 | 13.375 | 13375 | 13375 | 13375 | 13375 | 1 | 1 | 0 | 0 | 13375 | 2025-09-30
MS-9020 Compressor Delivered |  | 2025-10-02 17:00 |  | 2025-10-03 17:00 |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-10-31
PRO-3090 Compressor Received | 2025-10-01 08:00 | 2025-10-01 17:00 | 2025-10-01 08:00 | 2025-10-06 17:00 |  | 1 |  |  | 1 | 0.375 | 5.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-10-31
CON-4140 Pour Foundations | 2025-10-16 08:00 | 2025-10-30 17:00 | 2025-10-16 08:00 | 2025-10-31 08:00 | CIV - Concrete Crew | 1 | 135 |  | 3 | 14.375 | 15 | 46575 | 48600 | 46575 | 46575 | 0.95833 | 1 | -2025 | 0 | 48600 | 2025-10-31
CON-4200 Erect Columns | 2025-09-30 08:00 | 2025-10-09 17:00 | 2025-10-27 08:00 | 2025-11-05 17:00 | STR - Steel Erection Crew | 1 | 140 |  | 3 | 9.375 | 9.375 | 31500 | 31500 | 31500 | 31500 | 1 | 1 | 0 | 0 | 31500 | 2025-10-31
CON-4300 Receive Equipment | 2025-10-02 08:00 | 2025-10-06 17:00 | 2025-10-02 08:00 | 2025-10-06 17:00 | MECH - Rigging Crew | 1 | 135 |  | 3 | 4.375 | 4.375 | 14175 | 14175 | 14175 | 14175 | 1 | 1 | 0 | 0 | 14175 | 2025-10-31
PL-5120 Mainline Welding | 2025-09-18 08:00 | 2025-10-21 17:00 | 2025-09-18 08:00 | 2025-10-21 17:00 | PIPE - Welding Crew | 1 | 155 |  | 6 | 33.375 | 33.375 | 248310 | 248310 | 248310 | 248310 | 1 | 1 | 0 | 0 | 248310 | 2025-10-31
PL-5220 Tie-In Spools Fab | 2025-10-22 08:00 | 2025-10-29 17:00 | 2025-10-22 08:00 | 2025-10-29 17:00 | PIPE - Welding Crew | 1 | 155 |  | 1 | 7.375 | 7.375 | 9145 | 9145 | 9145 | 9145 | 1 | 1 | 0 | 0 | 9145 | 2025-10-31
CON-4150 Cure& Backfill | 2025-10-31 08:00 | 2025-11-12 17:00 | 2025-10-31 08:00 | 2025-11-12 17:00 | CIV - Concrete Crew | 1 | 135 |  | 3 | 12.375 | 12.375 | 40095 | 40095 | 40095 | 40095 | 1 | 1 | 0 | 0 | 40095 | 2025-11-30
CON-4210 Erect Beams | 2025-10-10 08:00 | 2025-11-07 17:00 | 2025-11-05 08:00 | 2025-12-03 17:00 | STR - Steel Erection Crew | 1 | 140 |  | 4 | 28.375 | 28.375 | 127120 | 127120 | 127120 | 127120 | 1 | 1 | 0 | 0 | 127120 | 2025-11-30
CON-4230 Install Pipe Rack Steel | 2025-11-10 08:00 | 2025-11-27 17:00 | 2025-12-22 08:00 | 2026-01-02 08:00 | STR - Steel Erection Crew | 1 | 140 |  | 3 | 17.375 | 11 | 58380 | 36960 | 58380 | 58380 | 1.5795 | 1 | 21420 | 0 | 36960 | 2025-11-30
PL-5130 Mainline NDT | 2025-10-22 08:00 | 2025-11-12 17:00 | 2025-10-22 08:00 | 2025-11-12 17:00 | PIPE - NDT Crew | 1 | 155 |  | 3 | 21.375 | 21.375 | 79515 | 79515 | 79515 | 79515 | 1 | 1 | 0 | 0 | 79515 | 2025-11-30
CON-4220 Install Grating | 2025-12-03 08:00 | 2025-12-22 17:00 | 2025-12-03 08:00 | 2025-12-22 17:00 | STR - Steel Erection Crew | 1 | 140 |  | 4 | 19.375 | 19.375 | 86800 | 86800 | 86800 | 86800 | 1 | 1 | 0 | 0 | 86800 | 2025-12-31
CON-4310 Set Vessels | 2025-11-28 08:00 | 2025-12-10 17:00 | 2026-01-02 08:00 | 2026-01-14 17:00 | MECH - Equipment Setting Crew | 1 | 140 |  | 1 | 12.375 | 12.375 | 13860 | 13860 | 13860 | 13860 | 1 | 1 | 0 | 0 | 13860 | 2025-12-31
CON-4330 Set Compressor | 2025-11-28 08:00 | 2025-12-12 17:00 | 2026-01-02 08:00 | 2026-01-16 17:00 | MECH - Equipment Setting Crew | 1 | 140 |  | 1 | 14.375 | 14.375 | 16100 | 16100 | 16100 | 16100 | 1 | 1 | 0 | 0 | 16100 | 2025-12-31
CON-4350 Install Spools (Area A) | 2025-11-28 08:00 | 2025-12-18 17:00 | 2026-01-02 08:00 | 2026-01-22 17:00 | MECH - Pipefitters Crew | 1 | 140 |  | 4 | 20.375 | 20.375 | 91280 | 91280 | 91280 | 91280 | 1 | 1 | 0 | 0 | 91280 | 2025-12-31
CON-4360 Install Spools (Area B) | 2025-11-28 08:00 | 2025-12-24 17:00 | 2026-01-02 08:00 | 2026-01-28 17:00 | MECH - Pipefitters Crew | 1 | 140 |  | 4 | 26.375 | 26.375 | 118160 | 118160 | 118160 | 118160 | 1 | 1 | 0 | 0 | 118160 | 2025-12-31
CON-4510 Install Cable Tray | 2025-11-28 08:00 | 2025-12-23 17:00 | 2026-01-02 08:00 | 2026-01-27 17:00 | E&I - Cable Tray Crew | 1 | 135 |  | 3 | 25.375 | 25.375 | 82215 | 82215 | 82215 | 82215 | 1 | 1 | 0 | 0 | 82215 | 2025-12-31
PL-5140 Field Joint Coating | 2025-11-13 08:00 | 2025-12-01 17:00 | 2025-11-13 08:00 | 2025-12-01 17:00 | PIPE - Coating Crew | 1 | 135 |  | 3 | 18.375 | 18.375 | 59535 | 59535 | 59535 | 59535 | 1 | 1 | 0 | 0 | 59535 | 2025-12-31
PL-5150 Lower-In | 2025-12-02 08:00 | 2025-12-22 17:00 | 2025-12-02 08:00 | 2025-12-22 17:00 | PIPE - Lower-In Crew | 1 | 135 |  | 3 | 20.375 | 20.375 | 66015 | 66015 | 66015 | 66015 | 1 | 1 | 0 | 0 | 66015 | 2025-12-31
CON-4320 Set Exchangers | 2026-01-02 08:00 | 2026-01-16 17:00 | 2026-01-02 08:00 | 2026-01-16 17:00 | MECH - Equipment Setting Crew | 1 | 140 |  | 1 | 14.375 | 14.375 | 16100 | 16100 | 16100 | 16100 | 1 | 1 | 0 | 0 | 16100 | 2026-01-31
CON-4340 Install Skid Piping | 2025-12-15 08:00 | 2026-01-01 17:00 | 2026-01-16 08:00 | 2026-02-04 17:00 | MECH - Pipefitters Crew | 1 | 140 |  | 3 | 17.375 | 19.375 | 58380 | 65100 | 58380 | 58380 | 0.89677 | 1 | -6720 | 0 | 65100 | 2026-01-31
CON-4370 Install Valves | 2025-12-25 08:00 | 2026-01-12 17:00 | 2026-01-28 08:00 | 2026-02-13 17:00 | MECH - Pipefitters Crew | 1 | 140 |  | 4 | 18.375 | 16.375 | 82320 | 73360 | 82320 | 82320 | 1.1221 | 1 | 8960 | 0 | 73360 | 2026-01-31
CON-4520 Pull Power Cables | 2025-12-24 08:00 | 2026-01-22 17:00 | 2026-01-27 08:00 | 2026-02-25 17:00 | E&I - Cable Pull Crew | 1 | 135 |  | 3 | 29.375 | 29.375 | 95175 | 95175 | 95175 | 95175 | 1 | 1 | 0 | 0 | 95175 | 2026-01-31
CON-4530 Pull Control Cables | 2025-12-24 08:00 | 2026-01-15 17:00 | 2026-01-27 08:00 | 2026-02-18 17:00 | E&I - Cable Pull Crew | 1 | 135 |  | 3 | 22.375 | 22.375 | 72495 | 72495 | 72495 | 72495 | 1 | 1 | 0 | 0 | 72495 | 2026-01-31
CON-4600 Install Instruments | 2025-12-25 08:00 | 2026-01-21 17:00 | 2026-01-28 | 2026-02-25 08:00 | E&I - Instrument Crew | 1 | 145 |  | 3 | 27.375 | 28.3333 | 95265 | 98600 | 95265 | 95265 | 0.96618 | 1 | -3335 | 0 | 98600 | 2026-01-31
CON-4620 Install Analyzers | 2026-01-02 08:00 | 2026-01-15 17:00 | 2026-01-02 08:00 | 2026-01-16 17:00 | E&I - Instrument Crew | 1 | 145 |  | 1 | 13.375 | 14.375 | 15515 | 16675 | 15515 | 15515 | 0.93043 | 1 | -1160 | 0 | 16675 | 2026-01-31
CON-4700 Paint Touch-Up | 2025-12-25 08:00 | 2026-01-19 17:00 | 2026-02-13 08:00 |  | MECH - Pipefitters Crew | 0 | 140 |  | 1 | 25.375 | 0 | 28420 | 0 | 28420 | 0 |  | 0 | 0 | -28420 | 28420 | 2026-01-31
CON-4810 Prefab Complete | 2026-01-02 08:00 |  | 2026-02-05 08:00 |  |  | 1 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-01-31
PL-5160 Backfill | 2025-12-23 08:00 | 2026-01-12 17:00 | 2025-12-23 08:00 | 2026-01-12 17:00 | PIPE - ROW Clearing Crew | 1 | 125 |  | 4 | 20.375 | 20.375 | 81500 | 81500 | 81500 | 81500 | 1 | 1 | 0 | 0 | 81500 | 2026-01-31
CON-4380 NDE / PWHT | 2026-01-13 08:00 | 2026-02-02 17:00 | 2026-02-13 08:00 | 2026-02-27 17:00 | MECH - NDE/NDT Technician | 1 | 150 |  | 1 | 20.375 | 14.375 | 24450 | 17250 | 24450 | 24450 | 1.4174 | 1 | 7200 | 0 | 17250 | 2026-02-28
CON-4390 Piping Hydrotest | 2026-02-03 08:00 | 2026-02-23 17:00 | 2026-02-27 08:00 | 2026-03-09 17:00 | PIPE - Hydrotest Crew | 1 | 135 |  | 1 | 20.375 | 10.375 | 22005 | 11205 | 22005 | 22005 | 1.9639 | 1 | 10800 | 0 | 11205 | 2026-02-28
CON-4540 MCC Terminations | 2026-01-23 08:00 | 2026-02-17 17:00 | 2026-02-25 08:00 | 2026-03-20 17:00 | E&I - Electrical Crew | 1 | 145 |  | 3 | 25.375 | 23.375 | 88305 | 81345 | 88305 | 88305 | 1.0856 | 1 | 6960 | 0 | 81345 | 2026-02-28
CON-4550 Field Terminations | 2026-01-16 08:00 | 2026-02-05 17:00 | 2026-02-18 08:00 |  | E&I - Termination Crew | 0.3 | 145 |  | 3 | 20.375 | 0 | 70905 | 0 | 70905 | 21271.5 |  | 0.3 | 21271.5 | -49633.5 | 49633.5 | 2026-02-28
CON-4560 Lighting& Heat Trace | 2026-01-23 08:00 | 2026-02-12 17:00 | 2026-02-25 08:00 |  | E&I - Electrical Crew | 0.4 | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 23635 | 9454 |  | 0.4 | 9454 | -14181 | 14181 | 2026-02-28
CON-4610 Install Control Valves | 2026-01-13 08:00 | 2026-02-09 17:00 | 2026-02-13 | 2026-03-26 17:00 | E&I - Instrument Crew | 1 | 145 |  | 1 | 27.375 | 41.7083 | 31755 | 48381.6667 | 31755 | 31755 | 0.65634 | 1 | -16626.6667 | 0 | 48381.6667 | 2026-02-28
CON-4630 Install Junction Boxes | 2026-01-27 08:00 | 2026-02-06 17:00 | 2026-01-27 08:00 | 2026-02-06 17:00 | E&I - Instrument Crew | 1 | 145 |  | 3 | 10.375 | 10.375 | 36105 | 36105 | 36105 | 36105 | 1 | 1 | 0 | 0 | 36105 | 2026-02-28
PL-5170 Install Valves | 2026-01-13 08:00 | 2026-02-02 17:00 | 2026-01-13 08:00 | 2026-02-02 17:00 | PIPE - Welding Crew | 1 | 155 |  | 1 | 20.375 | 20.375 | 25265 | 25265 | 25265 | 25265 | 1 | 1 | 0 | 0 | 25265 | 2026-02-28
MS-9040 Mech Completion (Pipeline) |  | 2026-03-27 17:00 |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-03-31
CON-4400 Drying& Reinstatement | 2026-03-09 08:00 | 2026-03-20 17:00 | 2026-03-09 08:00 | 2026-03-20 17:00 | MECH - Hydrotest Crew | 1 | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 12285 | 12285 | 1 | 1 | 0 | 0 | 12285 | 2026-03-31
CON-4570 Energize Substation | 2026-02-18 08:00 | 2026-03-10 17:00 |  |  | E&I - Electrical Crew | 0 | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 23635 | 0 |  | 0 | 0 | -23635 | 23635 | 2026-03-31
CON-4640 Loop Checks | 2026-03-11 08:00 | 2026-03-24 17:00 |  |  | COM - Controls/Loop Check Team | 0 | 145 |  | 1 | 13.375 | 0 | 15515 | 0 | 15515 | 0 |  | 0 | 0 | -15515 | 15515 | 2026-03-31
CON-4710 Insulation Install | 2026-02-24 08:00 | 2026-03-09 17:00 |  |  | MECH - Pipefitters Crew | 0 | 140 |  | 1 | 13.375 | 0 | 14980 | 0 | 14980 | 0 |  | 0 | 0 | -14980 | 14980 | 2026-03-31
CON-4720 Tagging& Labels | 2026-03-10 08:00 | 2026-03-30 17:00 |  |  | MECH - Pipefitters Crew | 0 | 140 |  | 1 | 20.375 | 0 | 22820 | 0 | 22820 | 0 |  | 0 | 0 | -22820 | 22820 | 2026-03-31
PL-5300 Hydrotest Prep | 2026-02-03 08:00 | 2026-03-04 17:00 | 2026-02-03 08:00 | 2026-03-04 17:00 | PIPE - Hydrotest Crew | 1 | 135 |  | 1 | 29.375 | 29.375 | 31725 | 31725 | 31725 | 31725 | 1 | 1 | 0 | 0 | 31725 | 2026-03-31
PL-5310 Hydrotest | 2026-03-05 08:00 | 2026-03-09 17:00 | 2026-03-05 08:00 |  | PIPE - Hydrotest Crew | 0 | 135 |  | 1 | 4.375 | 0 | 4725 | 0 | 4725 | 0 |  | 0 | 0 | -4725 | 4725 | 2026-03-31
PL-5320 Dewater& Purge | 2026-03-10 08:00 | 2026-03-12 17:00 |  |  | PIPE - Hydrotest Crew | 0 | 135 |  | 1 | 2.375 | 0 | 2565 | 0 | 2565 | 0 |  | 0 | 0 | -2565 | 2565 | 2026-03-31
PL-5330 Final Tie-Ins | 2026-03-13 08:00 | 2026-03-19 17:00 |  |  | PIPE - Welding Crew | 0 | 155 |  | 1 | 6.375 | 0 | 7905 | 0 | 7905 | 0 |  | 0 | 0 | -7905 | 7905 | 2026-03-31
PL-5340 Pipeline Mech Completion | 2026-03-20 08:00 | 2026-03-26 17:00 |  |  | PIPE - Pipeline Superintendent | 0 | 140 |  | 1 | 6.375 | 0 | 7140 | 0 | 7140 | 0 |  | 0 | 0 | -7140 | 7140 | 2026-03-31
COM-6010 Flushing | 2026-03-10 08:00 | 2026-03-30 17:00 |  |  | MECH - Hydrotest Crew | 0 | 135 |  | 1 | 20.375 | 0 | 22005 | 0 | 22005 | 0 |  | 0 | 0 | -22005 | 22005 | 2026-03-31
COM-6020 Utilities Commissioning | 2026-03-11 08:00 | 2026-03-24 17:00 |  |  | COM - Commissioning Lead | 0 | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 17120 | 0 |  | 0 | 0 | -17120 | 17120 | 2026-03-31
COM-6030 Early Energization | 2026-03-11 08:00 | 2026-03-24 17:00 |  |  | COM - Commissioning Lead | 0 | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 17120 | 0 |  | 0 | 0 | -17120 | 17120 | 2026-03-31
CON-4650 Controls Testing | 2026-03-25 08:00 | 2026-04-14 17:00 |  |  | COM - Controls/Loop Check Team | 0 | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 23635 | 0 |  | 0 | 0 | -23635 | 23635 | 2026-04-30
CON-4800 Shutdown Planning | 2026-03-10 08:00 | 2026-04-20 17:00 |  |  | CON - Construction Manager | 0 | 145 |  | 1 | 41.375 | 0 | 47995 | 0 | 47995 | 0 |  | 0 | 0 | -47995 | 47995 | 2026-04-30
MS-9030 Mech Completion (Plant) |  | 2026-05-12 17:00 |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-05-31
CON-4820 Execute Tie-Ins | 2026-04-21 08:00 | 2026-05-04 17:00 |  |  | MECH - Welders Crew | 0 | 150 |  | 1 | 13.375 | 0 | 16050 | 0 | 16050 | 0 |  | 0 | 0 | -16050 | 16050 | 2026-05-31
CON-4830 Tie-Ins Complete | 2026-05-05 08:00 | 2026-05-11 17:00 |  |  | CON - QA/QC Inspector | 0 | 90 |  | 1 | 6.375 | 0 | 4590 | 0 | 4590 | 0 |  | 0 | 0 | -4590 | 4590 | 2026-05-31
CON-4840 Plant Mech Completion | 2026-05-12 08:00 |  |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-05-31
COM-6040 Controls Testing | 2026-04-15 08:00 | 2026-05-05 17:00 |  |  | COM - Controls/Loop Check Team | 0 | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 23635 | 0 |  | 0 | 0 | -23635 | 23635 | 2026-05-31
MS-9050 Ready for Start-Up | 2026-06-30 08:00 |  |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-06-30
COM-6000 Walkdowns | 2026-05-12 08:00 | 2026-06-15 17:00 |  |  | COM - Commissioning Lead | 0 | 160 |  | 1 | 34.375 | 0 | 44000 | 0 | 44000 | 0 |  | 0 | 0 | -44000 | 44000 | 2026-06-30
COM-6050 Cause& Effect Testing | 2026-05-06 08:00 | 2026-06-02 17:00 |  |  | COM - Controls/Loop Check Team | 0 | 145 |  | 1 | 27.375 | 0 | 31755 | 0 | 31755 | 0 |  | 0 | 0 | -31755 | 31755 | 2026-06-30
COM-6060 Pre-Comm Complete | 2026-06-16 08:00 | 2026-06-29 17:00 |  |  | COM - Commissioning Lead | 0 | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 17120 | 0 |  | 0 | 0 | -17120 | 17120 | 2026-06-30
COM-6100 Introduce Gas | 2026-06-30 08:00 | 2026-07-27 17:00 |  |  | COM - Operators/Start-Up Team | 0 | 120 |  | 1 | 27.375 | 0 | 26280 | 0 | 26280 | 0 |  | 0 | 0 | -26280 | 26280 | 2026-07-31
COM-6110 Start Compressor | 2026-07-28 08:00 | 2026-07-30 17:00 |  |  | COM - Operators/Start-Up Team | 0 | 120 |  | 1 | 2.375 | 0 | 2280 | 0 | 2280 | 0 |  | 0 | 0 | -2280 | 2280 | 2026-07-31
COM-6130 Ready for Start-Up | 2026-06-30 08:00 | 2026-07-06 17:00 |  |  | COM - Operators/Start-Up Team | 0 | 120 |  | 1 | 6.375 | 0 | 6120 | 0 | 6120 | 0 |  | 0 | 0 | -6120 | 6120 | 2026-07-31
MS-9060 First Gas | 2026-08-14 08:00 |  |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-08-31
MS-9070 Performance Test Complete |  | 2026-08-25 17:00 |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-08-31
COM-6120 Ramp to Stable Ops | 2026-07-31 08:00 | 2026-08-13 17:00 |  |  | COM - Operators/Start-Up Team | 0 | 120 |  | 1 | 13.375 | 0 | 12840 | 0 | 12840 | 0 |  | 0 | 0 | -12840 | 12840 | 2026-08-31
COM-6140 First Gas | 2026-08-14 08:00 |  |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-08-31
COM-6150 Performance Test | 2026-08-14 08:00 | 2026-08-24 17:00 |  |  | COM - Operators/Start-Up Team | 0 | 120 |  | 1 | 10.375 | 0 | 9960 | 0 | 9960 | 0 |  | 0 | 0 | -9960 | 9960 | 2026-08-31
MS-9080 Substantial Completion |  | 2026-09-22 17:00 |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-09-30
COM-6160 Performance Test Passed | 2026-08-25 08:00 | 2026-09-07 17:00 |  |  | COM - Commissioning Lead | 0 | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 17120 | 0 |  | 0 | 0 | -17120 | 17120 | 2026-09-30
CLO-7010 As-Builts | 2026-08-25 08:00 | 2026-09-21 17:00 |  |  | CLO - Turnover/As-Builts Team | 0 | 95 |  | 1 | 27.375 | 0 | 20805 | 0 | 20805 | 0 |  | 0 | 0 | -20805 | 20805 | 2026-09-30
CLO-7020 O&M Manuals | 2026-08-25 08:00 | 2026-09-21 17:00 |  |  | CLO - Turnover/As-Builts Team | 0 | 95 |  | 1 | 27.375 | 0 | 20805 | 0 | 20805 | 0 |  | 0 | 0 | -20805 | 20805 | 2026-09-30
CLO-7030 Training | 2026-08-25 08:00 | 2026-09-14 17:00 |  |  | CLO - Training Coordinator | 0 | 90 |  | 1 | 20.375 | 0 | 14670 | 0 | 14670 | 0 |  | 0 | 0 | -14670 | 14670 | 2026-09-30
MS-9090 Final Completion |  | 2026-10-20 17:00 |  |  |  | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-10-31
CLO-7000 Punchlist Close | 2026-09-22 08:00 | 2026-10-19 17:00 |  |  |  | 0 |  |  | 1 | 27.375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-10-31

## Project Controls Analysis
Project: | Alberta Oil and Gas Facility Expansion
Report Date: | 2026-03-06
Data Source: | Primavera P6 Schedule & Excel Earned Value Analysis
Metric:
BAC (Budget at Completion) | 73608565
PV (Planned Value) | 73144430
EV (Earned Value) | 72978010.406
AC (Actual Cost) | 72935840
CPI (Cost Performance Index) | 1.0006
SPI (Schedule Peformance Index) | 0.99772
Cost Variance | 42170.406
Schedule Variance | -166419.594
EAC (Estimate at Completion) | 73566030.2275
As of 03/06/2026 the project is slightly behind schedule but essentially on budget. Planned Value (PV) is $73.14M, Earned Value (EV) is $72.98M, and Actual Cost (AC) is $72.94M. This results in a CPI of 1.00, indicating cost performance is effectively on plan, and an SPI of 1.00 (slightly below 1.0), indicating minor schedule slippage. The current variances are CV = +$42k and SV = -$166k, so the project has earned marginally less work than planned by the data date, but at essentially the expected cost. The main schedule impact remains the earlier civil/construction delay, which pushed downstream activities, while cost performance appears stable because major spending has tracked closely with earned progress under the current reporting assumptions.

## Earned Value S-Curve
Date | Sum of PV | Sum of EV | Sum of AC | Cumulative PV | Cumulative EV | Cumulative AC
2024-09-30 | 0 | 0 | 0 | 0 | 0 | 0
2024-10-31 | 132830 | 132830 | 132830 | 132830 | 132830 | 132830
2024-11-30 | 2655570 | 2655570 | 2656930 | 2788400 | 2788400 | 2789760
2024-12-31 | 208325 | 208325 | 208325 | 2996725 | 2996725 | 2998085
2025-01-31 | 346815 | 346815 | 346815 | 3343540 | 3343540 | 3344900
2025-02-28 | 4779745 | 4779745 | 4779745 | 8123285 | 8123285 | 8124645
2025-03-31 | 136770 | 93894.906 | 41940 | 8260055 | 8217179.906 | 8166585
2025-04-30 | 88255 | 88255 | 92220 | 8348310 | 8305434.906 | 8258805
2025-05-31 | 71430 | 71430 | 77181.6667 | 8419740 | 8376864.906 | 8335986.6667
2025-06-30 | 85880 | 85625 | 85625 | 8505620 | 8462489.906 | 8421611.6667
2025-07-31 | 71170 | 71170 | 85736.6667 | 8576790 | 8533659.906 | 8507348.3333
2025-08-31 | 213260 | 213260 | 240100 | 8790050 | 8746919.906 | 8747448.3333
2025-09-30 | 62222940 | 62222940 | 62236440 | 71012990 | 70969859.906 | 70983888.3333
2025-10-31 | 349705 | 349705 | 351730 | 71362695 | 71319564.906 | 71335618.3333
2025-11-30 | 305110 | 305110 | 283690 | 71667805 | 71624674.906 | 71619308.3333
2025-12-31 | 533965 | 533965 | 533965 | 72201770 | 72158639.906 | 72153273.3333
2026-01-31 | 545170 | 516750 | 519005 | 72746940 | 72675389.906 | 72672278.3333
2026-02-28 | 322425 | 258610.5 | 219551.6667 | 73069365 | 72934000.406 | 72891830
2026-03-31 | 75065 | 44010 | 44010 | 73144430 | 72978010.406 | 72935840
2026-04-30 | 0 | 0 | 0 | 73144430 | 72978010.406 | 72935840
2026-05-31 | 0 | 0 | 0 | 73144430 | 72978010.406 | 72935840
2026-06-30 | 0 | 0 | 0 | 73144430 | 72978010.406 | 72935840
2026-07-31 | 0 | 0 | 0 | 73144430 | 72978010.406 | 72935840
2026-08-31 | 0 | 0 | 0 | 73144430 | 72978010.406 | 72935840
2026-09-30 | 0 | 0 | 0 | 73144430 | 72978010.406 | 72935840
2026-10-31 | 0 | 0 | 0 | 73144430 | 72978010.406 | 72935840
Grand Total | 73144430 | 72978010.406 | 72935840

## Project Data
*planned material costs = actual material costs,
Data Date: | 2026-03-08
Hours/Day | 8
Activity Name | BL Project Start | BL Project Finish | Actual Start | Actual Finish | Resources | % Work Complete | Labour Rate (per hour) | Material Cost | Utilization (%) | Baseline Duration (Days) | Actual Duration (Days) | BAC | AC | PV | EV | CPI | SPI | CV | SV | EAC | PV_Month
MS-9000 Project Kickoff | 2024-09-25 08:00 |  | 2024-09-25 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-09-30
MS-9010 IFC Issued (All Disciplines) |  | 2025-06-06 17:00 |  | 2025-06-09 17:00 |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
MS-9020 Compressor Delivered |  | 2025-10-02 17:00 |  | 2025-10-03 17:00 |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-10-31
MS-9030 Mech Completion (Plant) |  | 2026-05-12 17:00 |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-05-31
MS-9040 Mech Completion (Pipeline) |  | 2026-03-27 17:00 |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-03-31
MS-9050 Ready for Start-Up | 2026-06-30 08:00 |  |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-06-30
MS-9060 First Gas | 2026-08-14 08:00 |  |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-08-31
MS-9070 Performance Test Complete |  | 2026-08-25 17:00 |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-08-31
MS-9080 Substantial Completion |  | 2026-09-22 17:00 |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-09-30
MS-9090 Final Completion |  | 2026-10-20 17:00 |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-10-31
PM-1000 Notice to Proceed | 2024-09-25 08:00 |  |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-09-30
PM-1010 Controls Setup | 2024-09-25 08:00 | 2024-10-04 17:00 | 2024-09-25 08:00 | 2024-10-04 17:00 | PM - Project Controls Lead | 100% | 140 |  | 1 | 9.375 | 9.375 | 10500 | 10500 | 10500 | 10500 | 1 | 1 | 0 | 0 | 10500 | 2024-10-31
PM-1020 Baseline Schedule Build | 2024-10-07 08:00 | 2024-10-22 17:00 | 2024-10-07 08:00 | 2024-10-22 17:00 | PM - Scheduler | 100% | 120 |  | 1 | 15.375 | 15.375 | 14760 | 14760 | 14760 | 14760 | 1 | 1 | 0 | 0 | 14760 | 2024-10-31
PM-1030 Baseline Cost Load | 2024-10-07 08:00 | 2024-10-11 17:00 | 2024-10-07 08:00 | 2024-10-11 17:00 | PM - Cost Controller | 100% | 120 |  | 1 | 4.375 | 4.375 | 4200 | 4200 | 4200 | 4200 | 1 | 1 | 0 | 0 | 4200 | 2024-10-31
PM-1040 Baseline Approval | 2024-10-23 08:00 | 2024-10-24 17:00 | 2024-10-23 08:00 | 2024-10-24 17:00 | PM - Project Manager | 100% | 150 |  | 1 | 1.375 | 1.375 | 1650 | 1650 | 1650 | 1650 | 1 | 1 | 0 | 0 | 1650 | 2024-10-31
PM-1060 Change Control Setup | 2024-10-07 08:00 | 2024-10-16 17:00 | 2024-10-07 08:00 | 2024-10-16 17:00 | PM - Project Controls Lead | 100% | 140 |  | 1 | 9.375 | 9.375 | 10500 | 10500 | 10500 | 10500 | 1 | 1 | 0 | 0 | 10500 | 2024-10-31
PM-1070 Risk Register Setup | 2024-10-07 08:00 | 2024-10-09 17:00 | 2024-10-07 08:00 | 2024-10-09 17:00 | PM - Project Controls Lead | 100% | 140 |  | 1 | 2.375 | 2.375 | 2660 | 2660 | 2660 | 2660 | 1 | 1 | 0 | 0 | 2660 | 2024-10-31
PM-1080 Progress Measurement Plan | 2024-10-07 08:00 | 2024-10-09 17:00 | 2024-10-07 08:00 | 2024-10-09 17:00 | PM - Project Controls Lead | 100% | 140 |  | 1 | 2.375 | 2.375 | 2660 | 2660 | 2660 | 2660 | 1 | 1 | 0 | 0 | 2660 | 2024-10-31
ENG-1100 Engineering Kickoff | 2024-09-26 08:00 | 2024-10-07 17:00 | 2024-09-26 08:00 | 2024-10-07 17:00 | ENG - Engineering Manager | 100% | 145 |  | 1 | 11.375 | 11.375 | 13195 | 13195 | 13195 | 13195 | 1 | 1 | 0 | 0 | 13195 | 2024-10-31
ENG-1110 Finalize Basis of Design | 2024-10-07 08:00 | 2024-10-17 17:00 | 2024-10-07 08:00 | 2024-10-17 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 10.375 | 10.375 | 11205 | 11205 | 11205 | 11205 | 1 | 1 | 0 | 0 | 11205 | 2024-10-31
ENG-1120 Design Criteria | 2024-10-18 08:00 | 2024-10-29 17:00 | 2024-10-18 08:00 | 2024-10-29 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 12285 | 12285 | 1 | 1 | 0 | 0 | 12285 | 2024-10-31
ENG-1130 Model Setup | 2024-10-07 08:00 | 2024-10-16 17:00 | 2024-10-07 08:00 | 2024-10-16 17:00 | ENG - CAD/Designer | 100% | 85 |  | 1 | 9.375 | 9.375 | 6375 | 6375 | 6375 | 6375 | 1 | 1 | 0 | 0 | 6375 | 2024-10-31
ENG-1140 30% Design Review | 2025-02-05 08:00 | 2025-02-14 17:00 | 2025-02-05 08:00 | 2025-02-14 17:00 | ENG - Engineering Manager | 100% | 145 |  | 1 | 9.375 | 9.375 | 10875 | 10875 | 10875 | 10875 | 1 | 1 | 0 | 0 | 10875 | 2025-02-28
ENG-1150 60% Design Review | 2025-04-10 08:00 | 2025-04-21 17:00 | 2025-04-10 08:00 | 2025-04-22 08:00 | ENG - Engineering Manager | 100% | 145 |  | 1 | 11.375 | 12 | 13195 | 13920 | 13195 | 13195 | 0.94792 | 1 | -725 | 0 | 13920 | 2025-04-30
ENG-1160 90% Design Review | 2025-05-21 08:00 | 2025-05-30 17:00 | 2025-05-21 | 2025-06-04 08:00 | ENG - Engineering Manager | 100% | 145 |  | 1 | 9.375 | 14.3333 | 10875 | 16626.6667 | 10875 | 10875 | 0.65407 | 1 | -5751.6667 | 0 | 16626.6667 | 2025-05-31
ENG-1200 PFD Development | 2024-10-18 08:00 | 2024-11-05 17:00 | 2024-10-18 08:00 | 2024-11-05 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 18.375 | 18.375 | 19845 | 19845 | 19845 | 19845 | 1 | 1 | 0 | 0 | 19845 | 2024-11-30
ENG-1210 Heat& Material Balance | 2024-11-08 08:00 | 2024-11-21 17:00 | 2024-11-08 08:00 | 2024-11-21 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2024-11-30
ENG-1220 P&ID Development | 2024-11-20 08:00 | 2024-12-26 17:00 | 2024-11-20 08:00 | 2024-12-26 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 36.375 | 36.375 | 39285 | 39285 | 39285 | 39285 | 1 | 1 | 0 | 0 | 39285 | 2024-12-31
ENG-1230 Control Philosophy | 2024-12-30 08:00 | 2025-01-10 17:00 | 2024-12-30 08:00 | 2025-01-10 17:00 | ENG - Instrument/Controls Engineer | 100% | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 12285 | 12285 | 1 | 1 | 0 | 0 | 12285 | 2025-01-31
ENG-1240 Relief Review | 2024-12-27 08:00 | 2025-01-02 17:00 | 2024-12-27 08:00 | 2025-01-02 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 6.375 | 6.375 | 6885 | 6885 | 6885 | 6885 | 1 | 1 | 0 | 0 | 6885 | 2025-01-31
ENG-1250 Cause& Effect Draft | 2025-01-10 08:00 | 2025-01-27 17:00 | 2025-01-10 08:00 | 2025-01-27 17:00 | ENG - Instrument/Controls Engineer | 100% | 135 |  | 1 | 17.375 | 17.375 | 18765 | 18765 | 18765 | 18765 | 1 | 1 | 0 | 0 | 18765 | 2025-01-31
ENG-1260 HAZOP Prep | 2024-12-27 08:00 | 2024-12-31 17:00 | 2024-12-27 08:00 | 2024-12-31 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 4.375 | 4.375 | 4725 | 4725 | 4725 | 4725 | 1 | 1 | 0 | 0 | 4725 | 2024-12-31
ENG-1270 HAZOP Session | 2024-12-31 08:00 | 2025-01-09 17:00 | 2024-12-31 08:00 | 2025-01-09 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 9.375 | 9.375 | 10125 | 10125 | 10125 | 10125 | 1 | 1 | 0 | 0 | 10125 | 2025-01-31
ENG-1280 HAZOP Closeout | 2025-01-10 08:00 | 2025-01-28 17:00 | 2025-01-10 08:00 | 2025-01-28 17:00 | ENG - Process Engineer | 100% | 135 |  | 1 | 18.375 | 18.375 | 19845 | 19845 | 19845 | 19845 | 1 | 1 | 0 | 0 | 19845 | 2025-01-31
ENG-1300 Equipment List | 2024-12-27 08:00 | 2025-01-14 17:00 | 2024-12-27 08:00 | 2025-01-14 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 18.375 | 18.375 | 19845 | 19845 | 19845 | 19845 | 1 | 1 | 0 | 0 | 19845 | 2025-01-31
ENG-1310 Compressor Datasheets | 2025-01-15 08:00 | 2025-01-29 17:00 | 2025-01-15 08:00 | 2025-01-29 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2025-01-31
ENG-1320 Separator Datasheets | 2025-01-15 08:00 | 2025-01-29 17:00 | 2025-01-15 08:00 | 2025-01-29 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2025-01-31
ENG-1330 Dehydration Datasheets | 2025-01-15 08:00 | 2025-01-28 17:00 | 2025-01-15 08:00 | 2025-01-28 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2025-01-31
ENG-1340 Cooler Datasheets | 2025-01-15 08:00 | 2025-01-28 17:00 | 2025-01-15 08:00 | 2025-01-28 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2025-01-31
ENG-1350 Valve List | 2025-01-22 08:00 | 2025-01-29 17:00 | 2025-01-22 08:00 | 2025-01-29 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 7.375 | 7.375 | 7965 | 7965 | 7965 | 7965 | 1 | 1 | 0 | 0 | 7965 | 2025-01-31
ENG-1360 Line List | 2024-12-27 08:00 | 2025-01-21 17:00 | 2024-12-27 08:00 | 2025-01-21 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 25.375 | 25.375 | 27405 | 27405 | 27405 | 27405 | 1 | 1 | 0 | 0 | 27405 | 2025-01-31
ENG-1370 Piping Classes | 2025-01-22 08:00 | 2025-02-07 17:00 | 2025-01-22 08:00 | 2025-02-07 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2025-02-28
ENG-1380 BIM Model 30% | 2025-02-10 08:00 | 2025-03-03 17:00 | 2025-02-10 08:00 | 2025-03-03 17:00 | ENG - CAD/Designer | 100% | 85 |  | 1 | 21.375 | 21.375 | 14535 | 14535 | 14535 | 14535 | 1 | 1 | 0 | 0 | 14535 | 2025-03-31
ENG-1390 BIM Model 60% | 2025-03-04 08:00 | 2025-03-31 17:00 | 2025-03-04 08:00 |  | ENG - CAD/Designer | 10% | 85 |  | 1 | 27.375 | 0 | 18615 | 0 | 18615 | 1861.5 |  | 0.1 | 1861.5 | -16753.5 | 16753.5 | 2025-03-31
ENG-1400 BIM Model 90% | 2025-04-01 08:00 | 2025-05-01 17:00 | 2025-04-01 08:00 | 2025-05-01 17:00 | ENG - CAD/Designer | 100% | 85 |  | 1 | 30.375 | 30.375 | 20655 | 20655 | 20655 | 20655 | 1 | 1 | 0 | 0 | 20655 | 2025-05-31
ENG-1410 Isometrics Issued | 2025-05-02 08:00 | 2025-05-20 17:00 | 2025-05-02 08:00 | 2025-05-20 17:00 | ENG - CAD/Designer | 100% | 85 |  | 1 | 18.375 | 18.375 | 12495 | 12495 | 12495 | 12495 | 1 | 1 | 0 | 0 | 12495 | 2025-05-31
ENG-1420 Pipe Support Design | 2025-05-21 08:00 | 2025-06-05 17:00 | 2025-05-21 08:00 | 2025-06-05 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 15.375 | 15.375 | 16605 | 16605 | 16605 | 16605 | 1 | 1 | 0 | 0 | 16605 | 2025-06-30
ENG-1430 Mech Package IFC Issued |  | 2025-06-06 17:00 |  | 2025-06-06 17:00 |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
ENG-1500 Site Survey | 2024-10-07 08:00 | 2024-10-15 17:00 | 2024-10-07 08:00 | 2024-10-15 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 8.375 | 8.375 | 9045 | 9045 | 9045 | 9045 | 1 | 1 | 0 | 0 | 9045 | 2024-10-31
ENG-1510 Geotech Review | 2024-10-16 08:00 | 2024-10-22 17:00 | 2024-10-16 08:00 | 2024-10-22 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 6.375 | 6.375 | 6885 | 6885 | 6885 | 6885 | 1 | 1 | 0 | 0 | 6885 | 2024-10-31
ENG-1520 Grading Plan | 2024-10-23 08:00 | 2024-11-08 17:00 | 2024-10-23 08:00 | 2024-11-08 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2024-11-30
ENG-1530 Foundations Design | 2024-10-23 08:00 | 2024-11-19 17:00 | 2024-10-23 08:00 | 2024-11-19 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 27.375 | 27.375 | 29565 | 29565 | 29565 | 29565 | 1 | 1 | 0 | 0 | 29565 | 2024-11-30
ENG-1540 Steel Design | 2024-11-20 08:00 | 2024-12-12 17:00 | 2024-11-20 08:00 | 2024-12-12 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 22.375 | 22.375 | 24165 | 24165 | 24165 | 24165 | 1 | 1 | 0 | 0 | 24165 | 2024-12-31
ENG-1550 Anchor Bolt Plans | 2024-12-13 08:00 | 2025-01-01 17:00 | 2024-12-13 08:00 | 2025-01-01 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 19.375 | 19.375 | 20925 | 20925 | 20925 | 20925 | 1 | 1 | 0 | 0 | 20925 | 2025-01-31
ENG-1560 Steel Connection Details | 2024-12-13 08:00 | 2024-12-26 17:00 | 2024-12-13 08:00 | 2024-12-26 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 13.375 | 13.375 | 14445 | 14445 | 14445 | 14445 | 1 | 1 | 0 | 0 | 14445 | 2024-12-31
ENG-1570 Structural IFC Issued |  | 2025-01-02 17:00 |  | 2025-01-02 17:00 |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-01-31
ENG-1600 Load Study | 2025-01-15 08:00 | 2025-02-04 17:00 | 2025-01-15 08:00 | 2025-02-04 17:00 | ENG - Electrical Engineer | 100% | 135 |  | 1 | 20.375 | 20.375 | 22005 | 22005 | 22005 | 22005 | 1 | 1 | 0 | 0 | 22005 | 2025-02-28
ENG-1610 Single-Line Diagrams | 2025-02-05 08:00 | 2025-02-26 17:00 | 2025-02-05 08:00 | 2025-02-26 17:00 | ENG - Electrical Engineer | 100% | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2025-02-28
ENG-1620 MCC Sizing | 2025-02-27 08:00 | 2025-03-12 17:00 | 2025-02-27 08:00 |  | ENG - Electrical Engineer | 40% | 135 |  | 1 | 13.375 | 0 | 14445 | 0 | 14445 | 5778 |  | 0.4 | 5778 | -8667 | 8667 | 2025-03-31
ENG-1630 Cable Schedule | 2025-03-13 08:00 | 2025-04-03 17:00 | 2025-03-13 08:00 | 2025-04-03 17:00 | ENG - Electrical Engineer | 100% | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2025-04-30
ENG-1640 Grounding Design | 2024-11-11 08:00 | 2024-11-25 17:00 | 2024-11-11 08:00 | 2024-11-25 17:00 | ENG - Electrical Engineer | 100% | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2024-11-30
ENG-1650 Area Classification | 2024-12-27 08:00 | 2025-01-08 17:00 | 2024-12-27 08:00 | 2025-01-08 17:00 | ENG - Electrical Engineer | 100% | 135 |  | 1 | 12.375 | 12.375 | 13365 | 13365 | 13365 | 13365 | 1 | 1 | 0 | 0 | 13365 | 2025-01-31
ENG-1660 Substation Upgrade | 2025-03-13 08:00 | 2025-04-09 17:00 | 2025-03-13 08:00 | 2025-04-10 17:00 | ENG - Electrical Engineer | 100% | 135 |  | 1 | 27.375 | 28.375 | 29565 | 30645 | 29565 | 29565 | 0.96476 | 1 | -1080 | 0 | 30645 | 2025-04-30
ENG-1670 Electrical IFC Issued | 2025-04-10 08:00 |  | 2025-04-10 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-04-30
ENG-1700 Instrument Index | 2024-12-27 08:00 | 2025-01-17 17:00 | 2024-12-27 08:00 | 2025-01-17 17:00 | ENG - Instrument/Controls Engineer | 100% | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2025-01-31
ENG-1710 IO List | 2025-01-20 08:00 | 2025-02-05 17:00 | 2025-01-20 08:00 | 2025-02-05 17:00 | ENG - Instrument/Controls Engineer | 100% | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2025-02-28
ENG-1720 Loop Diagrams | 2025-02-06 08:00 | 2025-03-07 17:00 | 2025-02-06 08:00 |  | ENG - Instrument/Controls Engineer | 90.91% | 135 |  | 1 | 29.375 | 0 | 31725 | 0 | 31725 | 28841.1975 |  | 0.9091 | 28841.1975 | -2883.8025 | 2883.8025 | 2025-03-31
ENG-1730 Control Narrative | 2025-01-10 08:00 | 2025-01-30 17:00 | 2025-01-10 08:00 | 2025-01-30 17:00 | ENG - Instrument/Controls Engineer | 100% | 135 |  | 1 | 20.375 | 20.375 | 22005 | 22005 | 22005 | 22005 | 1 | 1 | 0 | 0 | 22005 | 2025-01-31
ENG-1740 Cause& Effect Final | 2025-01-29 08:00 | 2025-02-14 17:00 | 2025-01-29 08:00 | 2025-02-14 17:00 | ENG - Instrument/Controls Engineer | 100% | 135 |  | 1 | 16.375 | 16.375 | 17685 | 17685 | 17685 | 17685 | 1 | 1 | 0 | 0 | 17685 | 2025-02-28
ENG-1750 DCS Architecture | 2025-02-10 08:00 | 2025-02-21 17:00 | 2025-02-10 08:00 | 2025-02-21 17:00 | ENG - Instrument/Controls Engineer | 100% | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 12285 | 12285 | 1 | 1 | 0 | 0 | 12285 | 2025-02-28
ENG-1760 Controls IFC Issued |  | 2025-03-10 17:00 |  | 2025-03-11 17:00 |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-03-31
ENG-1800 Route Selection | 2024-10-07 08:00 | 2024-10-21 17:00 | 2024-10-07 08:00 | 2024-10-21 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 14.375 | 14.375 | 15525 | 15525 | 15525 | 15525 | 1 | 1 | 0 | 0 | 15525 | 2024-10-31
ENG-1810 Environmental Screening | 2024-10-22 08:00 | 2024-11-12 17:00 | 2024-10-22 08:00 | 2024-11-12 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 21.375 | 21.375 | 23085 | 23085 | 23085 | 23085 | 1 | 1 | 0 | 0 | 23085 | 2024-11-30
ENG-1820 ROW Support | 2024-11-13 08:00 | 2024-12-11 17:00 | 2024-11-13 08:00 | 2024-12-11 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 28.375 | 28.375 | 30645 | 30645 | 30645 | 30645 | 1 | 1 | 0 | 0 | 30645 | 2024-12-31
ENG-1830 Watercourse Design | 2024-11-13 08:00 | 2024-12-05 17:00 | 2024-11-13 08:00 | 2024-12-05 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 22.375 | 22.375 | 24165 | 24165 | 24165 | 24165 | 1 | 1 | 0 | 0 | 24165 | 2024-12-31
ENG-1840 Wall Thickness Calc | 2024-10-22 08:00 | 2024-11-08 17:00 | 2024-10-22 08:00 | 2024-11-08 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 17.375 | 17.375 | 18765 | 18765 | 18765 | 18765 | 1 | 1 | 0 | 0 | 18765 | 2024-11-30
ENG-1850 Alignment Sheets Issued | 2024-12-06 08:00 | 2025-01-06 17:00 | 2024-12-06 08:00 | 2025-01-06 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 31.375 | 31.375 | 33885 | 33885 | 33885 | 33885 | 1 | 1 | 0 | 0 | 33885 | 2025-01-31
ENG-1860 Tie-In Details | 2025-01-07 08:00 | 2025-01-30 17:00 | 2025-01-07 08:00 | 2025-01-30 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 23.375 | 23.375 | 25245 | 25245 | 25245 | 25245 | 1 | 1 | 0 | 0 | 25245 | 2025-01-31
ENG-1870 Pipeline IFC Issued |  | 2025-01-31 17:00 |  | 2025-01-31 17:00 |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-01-31
REG-2000 Permit Strategy | 2024-09-25 08:00 | 2024-10-07 17:00 | 2024-09-25 08:00 | 2024-10-07 17:00 | REG - Permitting Lead | 100% | 115 |  | 1 | 12.375 | 12.375 | 11385 | 11385 | 11385 | 11385 | 1 | 1 | 0 | 0 | 11385 | 2024-10-31
REG-2010 Submit Approvals | 2025-01-31 08:00 | 2025-02-19 17:00 | 2025-01-31 08:00 | 2025-02-19 17:00 | REG - Permitting Lead | 100% | 115 |  | 1 | 19.375 | 19.375 | 17825 | 17825 | 17825 | 17825 | 1 | 1 | 0 | 0 | 17825 | 2025-02-28
REG-2020 Mitigation Plan | 2024-11-13 08:00 | 2024-12-04 17:00 | 2024-11-13 08:00 | 2024-12-04 17:00 | REG - Environmental Specialist | 100% | 105 |  | 1 | 21.375 | 21.375 | 17955 | 17955 | 17955 | 17955 | 1 | 1 | 0 | 0 | 17955 | 2024-12-31
REG-2030 Land Access Agreements | 2024-12-12 08:00 | 2025-02-10 17:00 | 2024-12-12 08:00 | 2025-02-10 17:00 | REG - Land Agent | 100% | 95 |  | 1 | 60.375 | 60.375 | 45885 | 45885 | 45885 | 45885 | 1 | 1 | 0 | 0 | 45885 | 2025-02-28
REG-2040 Indigenous Engagement | 2024-12-12 08:00 | 2025-02-20 17:00 | 2024-12-12 08:00 | 2025-02-20 17:00 | REG - Permitting Lead | 100% | 115 |  | 1 | 70.375 | 70.375 | 64745 | 64745 | 64745 | 64745 | 1 | 1 | 0 | 0 | 64745 | 2025-02-28
REG-2050 ROW Secured | 2025-02-21 08:00 | 2025-02-24 17:00 | 2025-02-21 08:00 | 2025-02-24 17:00 | REG - Land Agent | 100% | 95 |  | 1 | 3.375 | 3.375 | 2565 | 2565 | 2565 | 2565 | 1 | 1 | 0 | 0 | 2565 | 2025-02-28
REG-2060 Permits Approved | 2025-02-20 08:00 | 2025-02-21 17:00 | 2025-02-20 08:00 | 2025-02-21 17:00 |  | 100% |  |  | 1 | 1.375 | 1.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-02-28
PRO-3000 RFQ (Compressor) | 2025-01-30 08:00 | 2025-02-13 17:00 | 2025-01-30 08:00 | 2025-02-13 17:00 | PROC - Procurement Lead | 100% | 120 |  | 1 | 14.375 | 14.375 | 13800 | 13800 | 13800 | 13800 | 1 | 1 | 0 | 0 | 13800 | 2025-02-28
PRO-3010 Tech Eval (Compressor) | 2025-02-14 08:00 | 2025-02-21 17:00 | 2025-02-14 08:00 | 2025-02-21 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 7.375 | 7.375 | 7965 | 7965 | 7965 | 7965 | 1 | 1 | 0 | 0 | 7965 | 2025-02-28
PRO-3020 Comm Eval (Compressor) | 2025-02-24 08:00 | 2025-03-06 17:00 | 2025-02-24 08:00 |  | ENG - Mechanical Engineer | 88.89% | 135 |  | 1 | 10.375 | 0 | 11205 | 0 | 11205 | 9960.1245 |  | 0.8889 | 9960.1245 | -1244.8755 | 1244.8755 | 2025-03-31
PRO-3030 Compressor PO Award | 2025-03-07 08:00 |  | 2025-03-07 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-03-31
PRO-3030 Compressor Shop Drawings | 2025-03-07 08:00 | 2025-03-26 17:00 | 2025-03-07 08:00 | 2025-04-01 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 19.375 | 25.375 | 20925 | 27405 | 20925 | 20925 | 0.76355 | 1 | -6480 | 0 | 27405 | 2025-03-31
PRO-3040 Vendor Review Cycle 1 | 2025-03-27 08:00 | 2025-04-08 17:00 | 2025-03-27 08:00 | 2025-04-10 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 12.375 | 14.375 | 13365 | 15525 | 13365 | 13365 | 0.86087 | 1 | -2160 | 0 | 15525 | 2025-04-30
PRO-3050 Vendor Review Cycle 2 | 2025-04-09 08:00 | 2025-04-17 17:00 | 2025-04-10 08:00 | 2025-04-18 17:00 | ENG - Mechanical Engineer | 100% | 135 |  | 1 | 8.375 | 8.375 | 9045 | 9045 | 9045 | 9045 | 1 | 1 | 0 | 0 | 9045 | 2025-04-30
PRO-3060 Compressor Fabrication | 2025-04-18 08:00 | 2025-09-16 17:00 | 2025-04-18 08:00 | 2025-09-16 17:00 | MAT - Compressor Package | 100% |  | 62000000 | 1 | 151.375 | 151.375 | 62000000 | 62000000 | 62000000 | 62000000 | 1 | 1 | 0 | 0 | 62000000 | 2025-09-30
PRO-3070 Compressor FAT | 2025-09-17 08:00 | 2025-09-18 17:00 | 2025-09-17 08:00 | 2025-09-18 17:00 | PROC - QA/QC Inspector | 100% | 90 |  | 1 | 1.375 | 1.375 | 990 | 990 | 990 | 990 | 1 | 1 | 0 | 0 | 990 | 2025-09-30
PRO-3080 Ship Compressor | 2025-09-19 08:00 | 2025-09-30 17:00 | 2025-09-19 08:00 | 2025-09-30 17:00 | PROC - Buyer/Expeditor | 100% | 85 |  | 1 | 11.375 | 11.375 | 7735 | 7735 | 7735 | 7735 | 1 | 1 | 0 | 0 | 7735 | 2025-09-30
PRO-3090 Compressor Received | 2025-10-01 08:00 | 2025-10-01 17:00 | 2025-10-01 08:00 | 2025-10-06 17:00 |  | 100% |  |  | 1 | 0.375 | 5.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-10-31
PRO-3100 RFQ (Structural Steel) | 2024-12-13 08:00 | 2024-12-20 17:00 | 2024-12-13 08:00 | 2024-12-20 17:00 | PROC - Procurement Lead | 100% | 120 |  | 1 | 7.375 | 7.375 | 7080 | 7080 | 7080 | 7080 | 1 | 1 | 0 | 0 | 7080 | 2024-12-31
PRO-3110 Steel Award | 2024-12-23 08:00 |  | 2024-12-23 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-12-31
PRO-3120 Steel Shop Drawings | 2024-12-23 08:00 | 2025-01-15 17:00 | 2024-12-23 08:00 | 2025-01-15 17:00 | ENG - Civil/Structural Engineer | 100% | 135 |  | 1 | 23.375 | 23.375 | 25245 | 25245 | 25245 | 25245 | 1 | 1 | 0 | 0 | 25245 | 2025-01-31
PRO-3140 Steel Fabrication | 2024-09-25 08:00 | 2024-11-08 17:00 | 2024-09-25 08:00 | 2024-11-08 17:00 | MAT - Structural Steel Supply | 100% |  | 2500000 | 1 | 44.375 | 44.375 | 2500000 | 2500000 | 2500000 | 2500000 | 1 | 1 | 0 | 0 | 2500000 | 2024-11-30
PRO-3150 Deliver Steel | 2024-11-11 08:00 | 2024-11-12 17:00 | 2025-03-14 08:00 | 2025-03-17 17:00 | PROC - Buyer/Expeditor | 100% | 85 |  | 1 | 1.375 | 3.375 | 935 | 2295 | 935 | 935 | 0.40741 | 1 | -1360 | 0 | 2295 | 2024-11-30
PRO-3160 RFQ (Piping Bulks) | 2025-02-10 08:00 | 2025-02-18 17:00 | 2025-03-17 08:00 | 2025-03-25 17:00 |  | 100% |  |  | 1 | 8.375 | 8.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-02-28
PRO-3170 Piping Bulks Award | 2025-02-19 08:00 | 2025-02-20 17:00 | 2025-03-25 08:00 | 2025-03-26 17:00 | PROC - Procurement Lead | 100% | 120 |  | 1 | 1.375 | 1.375 | 1320 | 1320 | 1320 | 1320 | 1 | 1 | 0 | 0 | 1320 | 2025-02-28
PRO-3180 Receive Piping Bulks | 2025-02-21 08:00 | 2025-03-19 17:00 | 2025-02-21 08:00 |  | PROC - Procurement Lead | 47.37% | 120 |  | 1 | 26.375 | 0 | 25320 | 0 | 25320 | 11994.084 |  | 0.4737 | 11994.084 | -13325.916 | 13325.916 | 2025-03-31
PRO-3190 RFQ (E&I Bulks) | 2025-04-04 08:00 | 2025-04-10 17:00 | 2025-03-26 08:00 | 2025-04-11 17:00 |  | 100% |  |  | 1 | 6.375 | 16.375 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-04-30
PRO-3200 E&I Bulks Award | 2025-04-11 08:00 |  | 2025-04-11 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-04-30
PRO-3205 Electrical Shop Drawings | 2025-04-11 08:00 | 2025-05-06 17:00 | 2025-04-11 08:00 | 2025-05-06 17:00 | ENG - Electrical Engineer | 100% | 135 |  | 1 | 25.375 | 25.375 | 27405 | 27405 | 27405 | 27405 | 1 | 1 | 0 | 0 | 27405 | 2025-05-31
PRO-3210 Receive E&I Bulks | 2025-05-07 08:00 | 2025-06-19 17:00 | 2025-05-07 08:00 | 2025-06-19 17:00 | PROC - Buyer/Expeditor | 100% | 85 |  | 1 | 43.375 | 43.375 | 29495 | 29495 | 29495 | 29495 | 1 | 1 | 0 | 0 | 29495 | 2025-06-30
PRO-3300 RFQ (Line Pipe) | 2024-11-11 08:00 | 2024-11-27 17:00 | 2024-11-11 08:00 | 2024-11-27 17:00 | PROC - Procurement Lead | 100% | 120 |  | 1 | 16.375 | 16.375 | 15720 | 15720 | 15720 | 15720 | 1 | 1 | 0 | 0 | 15720 | 2024-11-30
PRO-3310 Line Pipe Award | 2024-11-28 08:00 |  | 2024-11-28 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2024-11-30
PRO-3315 Line Pipe Mill Data / Coating Submittals | 2024-11-28 08:00 | 2024-12-26 17:00 | 2024-11-28 08:00 | 2024-12-26 17:00 | ENG - Pipeline Engineer | 100% | 135 |  | 1 | 28.375 | 28.375 | 30645 | 30645 | 30645 | 30645 | 1 | 1 | 0 | 0 | 30645 | 2024-12-31
PRO-3320 Line Pipe Coating | 2024-12-27 08:00 | 2025-02-17 17:00 | 2024-12-27 08:00 | 2025-02-17 17:00 | MAT - Line Pipe Supply | 100% |  | 4500000 | 1 | 52.375 | 52.375 | 4500000 | 4500000 | 4500000 | 4500000 | 1 | 1 | 0 | 0 | 4500000 | 2025-02-28
PRO-3330 Deliver Line Pipe | 2025-02-18 08:00 | 2025-02-24 17:00 | 2025-02-18 08:00 | 2025-02-24 17:00 | PROC - Buyer/Expeditor | 100% | 85 |  | 1 | 6.375 | 6.375 | 4335 | 4335 | 4335 | 4335 | 1 | 1 | 0 | 0 | 4335 | 2025-02-28
PRO-3340 Receive Pipeline Valves | 2024-11-28 08:00 | 2024-12-20 17:00 | 2024-11-28 08:00 | 2024-12-20 17:00 | PROC - Buyer/Expeditor | 100% | 85 |  | 1 | 22.375 | 22.375 | 15215 | 15215 | 15215 | 15215 | 1 | 1 | 0 | 0 | 15215 | 2024-12-31
PRO-3400 Tender Civil Contractor | 2025-06-06 08:00 | 2025-06-25 17:00 | 2025-06-06 08:00 | 2025-06-25 17:00 | PM - Contracts/Admin | 100% | 85 |  | 1 | 19.375 | 19.375 | 13175 | 13175 | 13175 | 13175 | 1 | 1 | 0 | 0 | 13175 | 2025-06-30
PRO-3410 Civil Contractor Award | 2025-06-26 08:00 |  | 2025-06-26 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
PRO-3420 Tender Mechanical Contractor | 2025-06-06 08:00 | 2025-07-01 17:00 | 2025-06-06 08:00 | 2025-07-01 17:00 | PM - Contracts/Admin | 100% | 85 |  | 1 | 25.375 | 25.375 | 17255 | 17255 | 17255 | 17255 | 1 | 1 | 0 | 0 | 17255 | 2025-07-31
PRO-3430 Mechanical Contractor Award | 2025-07-02 08:00 |  | 2025-07-02 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-07-31
PRO-3440 Tender E&I Contractor | 2025-06-06 08:00 | 2025-06-26 17:00 | 2025-06-06 08:00 | 2025-06-26 17:00 | PM - Contracts/Admin | 100% | 85 |  | 1 | 20.375 | 20.375 | 13855 | 13855 | 13855 | 13855 | 1 | 1 | 0 | 0 | 13855 | 2025-06-30
PRO-3450 E&I Contractor Award | 2025-06-27 08:00 | 2025-06-27 17:00 | 2025-06-27 08:00 |  | PM - Contracts/Admin | 0% | 85 |  | 1 | 0.375 | 0 | 255 | 0 | 255 | 0 |  | 0 | 0 | -255 | 255 | 2025-06-30
PRO-3460 Tender Pipeline Contractor | 2025-06-06 08:00 | 2025-06-24 17:00 | 2025-06-06 08:00 | 2025-06-24 17:00 | PM - Contracts/Admin | 100% | 85 |  | 1 | 18.375 | 18.375 | 12495 | 12495 | 12495 | 12495 | 1 | 1 | 0 | 0 | 12495 | 2025-06-30
PRO-3470 Pipeline Contractor Award | 2025-06-25 08:00 |  | 2025-06-25 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2025-06-30
CON-4000 Plant Mobilization | 2025-06-26 08:00 | 2025-07-10 17:00 | 2025-06-26 08:00 | 2025-07-17 17:00 | CIV - Site Prep Crew | 100% | 120 |  | 1 | 14.375 | 21.375 | 13800 | 20520 | 13800 | 13800 | 0.67251 | 1 | -6720 | 0 | 20520 | 2025-07-31
CON-4010 Temp Facilities Setup | 2025-07-11 08:00 | 2025-07-22 17:00 | 2025-07-11 08:00 | 2025-07-24 17:00 | CIV - Site Prep Crew | 100% | 120 |  | 1 | 11.375 | 13.375 | 10920 | 12840 | 10920 | 10920 | 0.85047 | 1 | -1920 | 0 | 12840 | 2025-07-31
CON-4020 Survey& Layout | 2025-07-11 08:00 | 2025-07-15 17:00 | 2025-07-11 08:00 | 2025-07-18 17:00 | CIV - Site Prep Crew | 100% | 120 |  | 1 | 4.375 | 7.375 | 4200 | 7080 | 4200 | 4200 | 0.59322 | 1 | -2880 | 0 | 7080 | 2025-07-31
CON-4030 Clearing | 2025-07-16 08:00 | 2025-07-22 17:00 | 2025-07-18 08:00 | 2025-07-28 17:00 | CIV - Site Prep Crew | 100% | 120 |  | 1 | 6.375 | 10.375 | 6120 | 9960 | 6120 | 6120 | 0.61446 | 1 | -3840 | 0 | 9960 | 2025-07-31
CON-4100 Earthworks | 2025-07-23 08:00 | 2025-08-07 17:00 | 2025-07-28 08:00 | 2025-08-21 17:00 | CIV - Concrete Crew | 100% | 135 |  | 3 | 15.375 | 24.375 | 49815 | 78975 | 49815 | 49815 | 0.63077 | 1 | -29160 | 0 | 78975 | 2025-08-31
CON-4110 Underground Utilities | 2025-08-08 08:00 | 2025-09-08 17:00 | 2025-08-21 08:00 | 2025-09-19 17:00 | CIV - Concrete Crew | 100% | 135 |  | 3 | 31.375 | 29.375 | 101655 | 95175 | 101655 | 101655 | 1.0681 | 1 | 6480 | 0 | 95175 | 2025-09-30
CON-4120 Form Foundations | 2025-08-08 08:00 | 2025-08-26 17:00 | 2025-09-19 08:00 | 2025-10-07 17:00 | CIV - Concrete Crew | 100% | 135 |  | 3 | 18.375 | 18.375 | 59535 | 59535 | 59535 | 59535 | 1 | 1 | 0 | 0 | 59535 | 2025-08-31
CON-4130 Rebar Install | 2025-08-27 08:00 | 2025-09-01 17:00 | 2025-10-07 08:00 | 2025-10-17 08:00 | CIV - Concrete Crew | 100% | 135 |  | 4 | 5.375 | 10 | 23220 | 43200 | 23220 | 23220 | 0.5375 | 1 | -19980 | 0 | 43200 | 2025-09-30
CON-4140 Pour Foundations | 2025-10-16 08:00 | 2025-10-30 17:00 | 2025-10-16 08:00 | 2025-10-31 08:00 | CIV - Concrete Crew | 100% | 135 |  | 3 | 14.375 | 15 | 46575 | 48600 | 46575 | 46575 | 0.95833 | 1 | -2025 | 0 | 48600 | 2025-10-31
CON-4150 Cure& Backfill | 2025-10-31 08:00 | 2025-11-12 17:00 | 2025-10-31 08:00 | 2025-11-12 17:00 | CIV - Concrete Crew | 100% | 135 |  | 3 | 12.375 | 12.375 | 40095 | 40095 | 40095 | 40095 | 1 | 1 | 0 | 0 | 40095 | 2025-11-30
CON-4200 Erect Columns | 2025-09-30 08:00 | 2025-10-09 17:00 | 2025-10-27 08:00 | 2025-11-05 17:00 | STR - Steel Erection Crew | 100% | 140 |  | 3 | 9.375 | 9.375 | 31500 | 31500 | 31500 | 31500 | 1 | 1 | 0 | 0 | 31500 | 2025-10-31
CON-4210 Erect Beams | 2025-10-10 08:00 | 2025-11-07 17:00 | 2025-11-05 08:00 | 2025-12-03 17:00 | STR - Steel Erection Crew | 100% | 140 |  | 4 | 28.375 | 28.375 | 127120 | 127120 | 127120 | 127120 | 1 | 1 | 0 | 0 | 127120 | 2025-11-30
CON-4220 Install Grating | 2025-12-03 08:00 | 2025-12-22 17:00 | 2025-12-03 08:00 | 2025-12-22 17:00 | STR - Steel Erection Crew | 100% | 140 |  | 4 | 19.375 | 19.375 | 86800 | 86800 | 86800 | 86800 | 1 | 1 | 0 | 0 | 86800 | 2025-12-31
CON-4230 Install Pipe Rack Steel | 2025-11-10 08:00 | 2025-11-27 17:00 | 2025-12-22 08:00 | 2026-01-02 08:00 | STR - Steel Erection Crew | 100% | 140 |  | 3 | 17.375 | 11 | 58380 | 36960 | 58380 | 58380 | 1.5795 | 1 | 21420 | 0 | 36960 | 2025-11-30
CON-4300 Receive Equipment | 2025-10-02 08:00 | 2025-10-06 17:00 | 2025-10-02 08:00 | 2025-10-06 17:00 | MECH - Rigging Crew | 100% | 135 |  | 3 | 4.375 | 4.375 | 14175 | 14175 | 14175 | 14175 | 1 | 1 | 0 | 0 | 14175 | 2025-10-31
CON-4310 Set Vessels | 2025-11-28 08:00 | 2025-12-10 17:00 | 2026-01-02 08:00 | 2026-01-14 17:00 | MECH - Equipment Setting Crew | 100% | 140 |  | 1 | 12.375 | 12.375 | 13860 | 13860 | 13860 | 13860 | 1 | 1 | 0 | 0 | 13860 | 2025-12-31
CON-4320 Set Exchangers | 2026-01-02 08:00 | 2026-01-16 17:00 | 2026-01-02 08:00 | 2026-01-16 17:00 | MECH - Equipment Setting Crew | 100% | 140 |  | 1 | 14.375 | 14.375 | 16100 | 16100 | 16100 | 16100 | 1 | 1 | 0 | 0 | 16100 | 2026-01-31
CON-4330 Set Compressor | 2025-11-28 08:00 | 2025-12-12 17:00 | 2026-01-02 08:00 | 2026-01-16 17:00 | MECH - Equipment Setting Crew | 100% | 140 |  | 1 | 14.375 | 14.375 | 16100 | 16100 | 16100 | 16100 | 1 | 1 | 0 | 0 | 16100 | 2025-12-31
CON-4340 Install Skid Piping | 2025-12-15 08:00 | 2026-01-01 17:00 | 2026-01-16 08:00 | 2026-02-04 17:00 | MECH - Pipefitters Crew | 100% | 140 |  | 3 | 17.375 | 19.375 | 58380 | 65100 | 58380 | 58380 | 0.89677 | 1 | -6720 | 0 | 65100 | 2026-01-31
CON-4350 Install Spools (Area A) | 2025-11-28 08:00 | 2025-12-18 17:00 | 2026-01-02 08:00 | 2026-01-22 17:00 | MECH - Pipefitters Crew | 100% | 140 |  | 4 | 20.375 | 20.375 | 91280 | 91280 | 91280 | 91280 | 1 | 1 | 0 | 0 | 91280 | 2025-12-31
CON-4360 Install Spools (Area B) | 2025-11-28 08:00 | 2025-12-24 17:00 | 2026-01-02 08:00 | 2026-01-28 17:00 | MECH - Pipefitters Crew | 100% | 140 |  | 4 | 26.375 | 26.375 | 118160 | 118160 | 118160 | 118160 | 1 | 1 | 0 | 0 | 118160 | 2025-12-31
CON-4370 Install Valves | 2025-12-25 08:00 | 2026-01-12 17:00 | 2026-01-28 08:00 | 2026-02-13 17:00 | MECH - Pipefitters Crew | 100% | 140 |  | 4 | 18.375 | 16.375 | 82320 | 73360 | 82320 | 82320 | 1.1221 | 1 | 8960 | 0 | 73360 | 2026-01-31
CON-4380 NDE / PWHT | 2026-01-13 08:00 | 2026-02-02 17:00 | 2026-02-13 08:00 | 2026-02-27 17:00 | MECH - NDE/NDT Technician | 100% | 150 |  | 1 | 20.375 | 14.375 | 24450 | 17250 | 24450 | 24450 | 1.4174 | 1 | 7200 | 0 | 17250 | 2026-02-28
CON-4390 Piping Hydrotest | 2026-02-03 08:00 | 2026-02-23 17:00 | 2026-02-27 08:00 | 2026-03-09 17:00 | PIPE - Hydrotest Crew | 100% | 135 |  | 1 | 20.375 | 10.375 | 22005 | 11205 | 22005 | 22005 | 1.9639 | 1 | 10800 | 0 | 11205 | 2026-02-28
CON-4400 Drying& Reinstatement | 2026-03-09 08:00 | 2026-03-20 17:00 | 2026-03-09 08:00 | 2026-03-20 17:00 | MECH - Hydrotest Crew | 100% | 135 |  | 1 | 11.375 | 11.375 | 12285 | 12285 | 0 | 12285 | 1 |  | 0 | 12285 | 12285 | 2026-03-31
CON-4500 Install Ground Grid | 2025-08-08 08:00 | 2025-08-18 17:00 | 2025-08-21 08:00 | 2025-08-29 17:00 | E&I - Electrical Crew | 100% | 145 |  | 1 | 10.375 | 8.375 | 12035 | 9715 | 12035 | 12035 | 1.2388 | 1 | 2320 | 0 | 9715 | 2025-08-31
CON-4510 Install Cable Tray | 2025-11-28 08:00 | 2025-12-23 17:00 | 2026-01-02 08:00 | 2026-01-27 17:00 | E&I - Cable Tray Crew | 100% | 135 |  | 3 | 25.375 | 25.375 | 82215 | 82215 | 82215 | 82215 | 1 | 1 | 0 | 0 | 82215 | 2025-12-31
CON-4520 Pull Power Cables | 2025-12-24 08:00 | 2026-01-22 17:00 | 2026-01-27 08:00 | 2026-02-25 17:00 | E&I - Cable Pull Crew | 100% | 135 |  | 3 | 29.375 | 29.375 | 95175 | 95175 | 95175 | 95175 | 1 | 1 | 0 | 0 | 95175 | 2026-01-31
CON-4530 Pull Control Cables | 2025-12-24 08:00 | 2026-01-15 17:00 | 2026-01-27 08:00 | 2026-02-18 17:00 | E&I - Cable Pull Crew | 100% | 135 |  | 3 | 22.375 | 22.375 | 72495 | 72495 | 72495 | 72495 | 1 | 1 | 0 | 0 | 72495 | 2026-01-31
CON-4540 MCC Terminations | 2026-01-23 08:00 | 2026-02-17 17:00 | 2026-02-25 08:00 | 2026-03-20 17:00 | E&I - Electrical Crew | 100% | 145 |  | 3 | 25.375 | 23.375 | 88305 | 81345 | 88305 | 88305 | 1.0856 | 1 | 6960 | 0 | 81345 | 2026-02-28
CON-4550 Field Terminations | 2026-01-16 08:00 | 2026-02-05 17:00 | 2026-02-18 08:00 |  | E&I - Termination Crew | 30% | 145 |  | 3 | 20.375 | 0 | 70905 | 0 | 70905 | 21271.5 |  | 0.3 | 21271.5 | -49633.5 | 49633.5 | 2026-02-28
CON-4560 Lighting& Heat Trace | 2026-01-23 08:00 | 2026-02-12 17:00 | 2026-02-25 08:00 |  | E&I - Electrical Crew | 40% | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 23635 | 9454 |  | 0.4 | 9454 | -14181 | 14181 | 2026-02-28
CON-4570 Energize Substation | 2026-02-18 08:00 | 2026-03-10 17:00 |  |  | E&I - Electrical Crew | 0% | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 23635 | 0 |  | 0 | 0 | -23635 | 23635 | 2026-03-31
CON-4600 Install Instruments | 2025-12-25 08:00 | 2026-01-21 17:00 | 2026-01-28 | 2026-02-25 08:00 | E&I - Instrument Crew | 100% | 145 |  | 3 | 27.375 | 28.3333 | 95265 | 98600 | 95265 | 95265 | 0.96618 | 1 | -3335 | 0 | 98600 | 2026-01-31
CON-4610 Install Control Valves | 2026-01-13 08:00 | 2026-02-09 17:00 | 2026-02-13 | 2026-03-26 17:00 | E&I - Instrument Crew | 100% | 145 |  | 1 | 27.375 | 41.7083 | 31755 | 48381.6667 | 31755 | 31755 | 0.65634 | 1 | -16626.6667 | 0 | 48381.6667 | 2026-02-28
CON-4620 Install Analyzers | 2026-01-02 08:00 | 2026-01-15 17:00 | 2026-01-02 08:00 | 2026-01-16 17:00 | E&I - Instrument Crew | 100% | 145 |  | 1 | 13.375 | 14.375 | 15515 | 16675 | 15515 | 15515 | 0.93043 | 1 | -1160 | 0 | 16675 | 2026-01-31
CON-4630 Install Junction Boxes | 2026-01-27 08:00 | 2026-02-06 17:00 | 2026-01-27 08:00 | 2026-02-06 17:00 | E&I - Instrument Crew | 100% | 145 |  | 3 | 10.375 | 10.375 | 36105 | 36105 | 36105 | 36105 | 1 | 1 | 0 | 0 | 36105 | 2026-02-28
CON-4640 Loop Checks | 2026-03-11 08:00 | 2026-03-24 17:00 |  |  | COM - Controls/Loop Check Team | 0% | 145 |  | 1 | 13.375 | 0 | 15515 | 0 | 0 | 0 |  |  | 0 | 0 | 15515 | 2026-03-31
CON-4650 Controls Testing | 2026-03-25 08:00 | 2026-04-14 17:00 |  |  | COM - Controls/Loop Check Team | 0% | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 0 | 0 |  |  | 0 | 0 | 23635 | 2026-04-30
CON-4700 Paint Touch-Up | 2025-12-25 08:00 | 2026-01-19 17:00 | 2026-02-13 08:00 |  | MECH - Pipefitters Crew | 0% | 140 |  | 1 | 25.375 | 0 | 28420 | 0 | 28420 | 0 |  | 0 | 0 | -28420 | 28420 | 2026-01-31
CON-4710 Insulation Install | 2026-02-24 08:00 | 2026-03-09 17:00 |  |  | MECH - Pipefitters Crew | 0% | 140 |  | 1 | 13.375 | 0 | 14980 | 0 | 14980 | 0 |  | 0 | 0 | -14980 | 14980 | 2026-03-31
CON-4720 Tagging& Labels | 2026-03-10 08:00 | 2026-03-30 17:00 |  |  | MECH - Pipefitters Crew | 0% | 140 |  | 1 | 20.375 | 0 | 22820 | 0 | 0 | 0 |  |  | 0 | 0 | 22820 | 2026-03-31
CON-4800 Shutdown Planning | 2026-03-10 08:00 | 2026-04-20 17:00 |  |  | CON - Construction Manager | 0% | 145 |  | 1 | 41.375 | 0 | 47995 | 0 | 0 | 0 |  |  | 0 | 0 | 47995 | 2026-04-30
CON-4810 Prefab Complete | 2026-01-02 08:00 |  | 2026-02-05 08:00 |  |  | 100% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-01-31
CON-4820 Execute Tie-Ins | 2026-04-21 08:00 | 2026-05-04 17:00 |  |  | MECH - Welders Crew | 0% | 150 |  | 1 | 13.375 | 0 | 16050 | 0 | 0 | 0 |  |  | 0 | 0 | 16050 | 2026-05-31
CON-4830 Tie-Ins Complete | 2026-05-05 08:00 | 2026-05-11 17:00 |  |  | CON - QA/QC Inspector | 0% | 90 |  | 1 | 6.375 | 0 | 4590 | 0 | 0 | 0 |  |  | 0 | 0 | 4590 | 2026-05-31
CON-4840 Plant Mech Completion | 2026-05-12 08:00 |  |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-05-31
PL-5000 Pipeline Mobilization | 2025-06-25 08:00 | 2025-07-04 17:00 | 2025-06-25 08:00 | 2025-07-04 | PIPE - Pipeline Superintendent | 100% | 140 |  | 1 | 9.375 | 8.6667 | 10500 | 9706.6667 | 10500 | 10500 | 1.0817 | 1 | 793.3333 | 0 | 9706.6667 | 2025-07-31
PL-5010 Survey& Staking | 2025-07-07 08:00 | 2025-07-15 17:00 | 2025-07-07 08:00 | 2025-07-15 17:00 | PIPE - ROW Clearing Crew | 100% | 125 |  | 1 | 8.375 | 8.375 | 8375 | 8375 | 8375 | 8375 | 1 | 1 | 0 | 0 | 8375 | 2025-07-31
PL-5020 ROW Clearing | 2025-07-16 08:00 | 2025-08-04 17:00 | 2025-07-16 08:00 | 2025-08-04 17:00 | PIPE - ROW Clearing Crew | 100% | 125 |  | 4 | 19.375 | 19.375 | 77500 | 77500 | 77500 | 77500 | 1 | 1 | 0 | 0 | 77500 | 2025-08-31
PL-5030 Access Improvements | 2025-08-05 08:00 | 2025-08-19 17:00 | 2025-08-05 08:00 | 2025-08-19 17:00 | PIPE - ROW Clearing Crew | 100% | 125 |  | 1 | 14.375 | 14.375 | 14375 | 14375 | 14375 | 14375 | 1 | 1 | 0 | 0 | 14375 | 2025-08-31
PL-5100 Pipe Stringing | 2025-08-20 08:00 | 2025-09-05 17:00 | 2025-08-20 08:00 | 2025-09-05 17:00 | PIPE - Stringing Crew | 100% | 130 |  | 3 | 16.375 | 16.375 | 51090 | 51090 | 51090 | 51090 | 1 | 1 | 0 | 0 | 51090 | 2025-09-30
PL-5110 Pipe Bending | 2025-09-08 08:00 | 2025-09-17 17:00 | 2025-09-08 08:00 | 2025-09-17 17:00 | PIPE - Bending Crew | 100% | 140 |  | 1 | 9.375 | 9.375 | 10500 | 10500 | 10500 | 10500 | 1 | 1 | 0 | 0 | 10500 | 2025-09-30
PL-5120 Mainline Welding | 2025-09-18 08:00 | 2025-10-21 17:00 | 2025-09-18 08:00 | 2025-10-21 17:00 | PIPE - Welding Crew | 100% | 155 |  | 6 | 33.375 | 33.375 | 248310 | 248310 | 248310 | 248310 | 1 | 1 | 0 | 0 | 248310 | 2025-10-31
PL-5130 Mainline NDT | 2025-10-22 08:00 | 2025-11-12 17:00 | 2025-10-22 08:00 | 2025-11-12 17:00 | PIPE - NDT Crew | 100% | 155 |  | 3 | 21.375 | 21.375 | 79515 | 79515 | 79515 | 79515 | 1 | 1 | 0 | 0 | 79515 | 2025-11-30
PL-5140 Field Joint Coating | 2025-11-13 08:00 | 2025-12-01 17:00 | 2025-11-13 08:00 | 2025-12-01 17:00 | PIPE - Coating Crew | 100% | 135 |  | 3 | 18.375 | 18.375 | 59535 | 59535 | 59535 | 59535 | 1 | 1 | 0 | 0 | 59535 | 2025-12-31
PL-5150 Lower-In | 2025-12-02 08:00 | 2025-12-22 17:00 | 2025-12-02 08:00 | 2025-12-22 17:00 | PIPE - Lower-In Crew | 100% | 135 |  | 3 | 20.375 | 20.375 | 66015 | 66015 | 66015 | 66015 | 1 | 1 | 0 | 0 | 66015 | 2025-12-31
PL-5160 Backfill | 2025-12-23 08:00 | 2026-01-12 17:00 | 2025-12-23 08:00 | 2026-01-12 17:00 | PIPE - ROW Clearing Crew | 100% | 125 |  | 4 | 20.375 | 20.375 | 81500 | 81500 | 81500 | 81500 | 1 | 1 | 0 | 0 | 81500 | 2026-01-31
PL-5170 Install Valves | 2026-01-13 08:00 | 2026-02-02 17:00 | 2026-01-13 08:00 | 2026-02-02 17:00 | PIPE - Welding Crew | 100% | 155 |  | 1 | 20.375 | 20.375 | 25265 | 25265 | 25265 | 25265 | 1 | 1 | 0 | 0 | 25265 | 2026-02-28
PL-5200 Watercourse Crossing | 2025-08-20 08:00 | 2025-09-03 17:00 | 2025-08-20 08:00 | 2025-09-03 17:00 | PIPE - ROW Clearing Crew | 100% | 125 |  | 1 | 14.375 | 14.375 | 14375 | 14375 | 14375 | 14375 | 1 | 1 | 0 | 0 | 14375 | 2025-09-30
PL-5210 Road Crossing | 2025-08-20 08:00 | 2025-09-02 17:00 | 2025-08-20 08:00 | 2025-09-02 17:00 | PIPE - ROW Clearing Crew | 100% | 125 |  | 1 | 13.375 | 13.375 | 13375 | 13375 | 13375 | 13375 | 1 | 1 | 0 | 0 | 13375 | 2025-09-30
PL-5220 Tie-In Spools Fab | 2025-10-22 08:00 | 2025-10-29 17:00 | 2025-10-22 08:00 | 2025-10-29 17:00 | PIPE - Welding Crew | 100% | 155 |  | 1 | 7.375 | 7.375 | 9145 | 9145 | 9145 | 9145 | 1 | 1 | 0 | 0 | 9145 | 2025-10-31
PL-5300 Hydrotest Prep | 2026-02-03 08:00 | 2026-03-04 17:00 | 2026-02-03 08:00 | 2026-03-04 17:00 | PIPE - Hydrotest Crew | 100% | 135 |  | 1 | 29.375 | 29.375 | 31725 | 31725 | 31725 | 31725 | 1 | 1 | 0 | 0 | 31725 | 2026-03-31
PL-5310 Hydrotest | 2026-03-05 08:00 | 2026-03-09 17:00 | 2026-03-05 08:00 |  | PIPE - Hydrotest Crew | 0% | 135 |  | 1 | 4.375 | 0 | 4725 | 0 | 4725 | 0 |  | 0 | 0 | -4725 | 4725 | 2026-03-31
PL-5320 Dewater& Purge | 2026-03-10 08:00 | 2026-03-12 17:00 |  |  | PIPE - Hydrotest Crew | 0% | 135 |  | 1 | 2.375 | 0 | 2565 | 0 | 0 | 0 |  |  | 0 | 0 | 2565 | 2026-03-31
PL-5330 Final Tie-Ins | 2026-03-13 08:00 | 2026-03-19 17:00 |  |  | PIPE - Welding Crew | 0% | 155 |  | 1 | 6.375 | 0 | 7905 | 0 | 0 | 0 |  |  | 0 | 0 | 7905 | 2026-03-31
PL-5340 Pipeline Mech Completion | 2026-03-20 08:00 | 2026-03-26 17:00 |  |  | PIPE - Pipeline Superintendent | 0% | 140 |  | 1 | 6.375 | 0 | 7140 | 0 | 0 | 0 |  |  | 0 | 0 | 7140 | 2026-03-31
COM-6000 Walkdowns | 2026-05-12 08:00 | 2026-06-15 17:00 |  |  | COM - Commissioning Lead | 0% | 160 |  | 1 | 34.375 | 0 | 44000 | 0 | 0 | 0 |  |  | 0 | 0 | 44000 | 2026-06-30
COM-6010 Flushing | 2026-03-10 08:00 | 2026-03-30 17:00 |  |  | MECH - Hydrotest Crew | 0% | 135 |  | 1 | 20.375 | 0 | 22005 | 0 | 0 | 0 |  |  | 0 | 0 | 22005 | 2026-03-31
COM-6020 Utilities Commissioning | 2026-03-11 08:00 | 2026-03-24 17:00 |  |  | COM - Commissioning Lead | 0% | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 0 | 0 |  |  | 0 | 0 | 17120 | 2026-03-31
COM-6030 Early Energization | 2026-03-11 08:00 | 2026-03-24 17:00 |  |  | COM - Commissioning Lead | 0% | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 0 | 0 |  |  | 0 | 0 | 17120 | 2026-03-31
COM-6040 Controls Testing | 2026-04-15 08:00 | 2026-05-05 17:00 |  |  | COM - Controls/Loop Check Team | 0% | 145 |  | 1 | 20.375 | 0 | 23635 | 0 | 0 | 0 |  |  | 0 | 0 | 23635 | 2026-05-31
COM-6050 Cause& Effect Testing | 2026-05-06 08:00 | 2026-06-02 17:00 |  |  | COM - Controls/Loop Check Team | 0% | 145 |  | 1 | 27.375 | 0 | 31755 | 0 | 0 | 0 |  |  | 0 | 0 | 31755 | 2026-06-30
COM-6060 Pre-Comm Complete | 2026-06-16 08:00 | 2026-06-29 17:00 |  |  | COM - Commissioning Lead | 0% | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 0 | 0 |  |  | 0 | 0 | 17120 | 2026-06-30
COM-6100 Introduce Gas | 2026-06-30 08:00 | 2026-07-27 17:00 |  |  | COM - Operators/Start-Up Team | 0% | 120 |  | 1 | 27.375 | 0 | 26280 | 0 | 0 | 0 |  |  | 0 | 0 | 26280 | 2026-07-31
COM-6110 Start Compressor | 2026-07-28 08:00 | 2026-07-30 17:00 |  |  | COM - Operators/Start-Up Team | 0% | 120 |  | 1 | 2.375 | 0 | 2280 | 0 | 0 | 0 |  |  | 0 | 0 | 2280 | 2026-07-31
COM-6120 Ramp to Stable Ops | 2026-07-31 08:00 | 2026-08-13 17:00 |  |  | COM - Operators/Start-Up Team | 0% | 120 |  | 1 | 13.375 | 0 | 12840 | 0 | 0 | 0 |  |  | 0 | 0 | 12840 | 2026-08-31
COM-6130 Ready for Start-Up | 2026-06-30 08:00 | 2026-07-06 17:00 |  |  | COM - Operators/Start-Up Team | 0% | 120 |  | 1 | 6.375 | 0 | 6120 | 0 | 0 | 0 |  |  | 0 | 0 | 6120 | 2026-07-31
COM-6140 First Gas | 2026-08-14 08:00 |  |  |  |  | 0% |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-08-31
COM-6150 Performance Test | 2026-08-14 08:00 | 2026-08-24 17:00 |  |  | COM - Operators/Start-Up Team | 0% | 120 |  | 1 | 10.375 | 0 | 9960 | 0 | 0 | 0 |  |  | 0 | 0 | 9960 | 2026-08-31
COM-6160 Performance Test Passed | 2026-08-25 08:00 | 2026-09-07 17:00 |  |  | COM - Commissioning Lead | 0% | 160 |  | 1 | 13.375 | 0 | 17120 | 0 | 0 | 0 |  |  | 0 | 0 | 17120 | 2026-09-30
CLO-7000 Punchlist Close | 2026-09-22 08:00 | 2026-10-19 17:00 |  |  |  | 0% |  |  | 1 | 27.375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2026-10-31
CLO-7010 As-Builts | 2026-08-25 08:00 | 2026-09-21 17:00 |  |  | CLO - Turnover/As-Builts Team | 0% | 95 |  | 1 | 27.375 | 0 | 20805 | 0 | 0 | 0 |  |  | 0 | 0 | 20805 | 2026-09-30
CLO-7020 O&M Manuals | 2026-08-25 08:00 | 2026-09-21 17:00 |  |  | CLO - Turnover/As-Builts Team | 0% | 95 |  | 1 | 27.375 | 0 | 20805 | 0 | 0 | 0 |  |  | 0 | 0 | 20805 | 2026-09-30
CLO-7030 Training | 2026-08-25 08:00 | 2026-09-14 17:00 |  |  | CLO - Training Coordinator | 0% | 90 |  | 1 | 20.375 | 0 | 14670 | 0 | 0 | 0 |  |  | 0 | 0 | 14670 | 2026-09-30
[12 empty] | 73608565 | 72935840 | 73144430 | 72978010.406
Formulas:
PV_Month = EOMONTH(IF([BL Project Finish]="",[BL Project Start],[BL Project Finish]),0)

## Resource Sheet (hidden)
Initials | Group | Labour Resource | Material Resource | Max. Units | Std. Rate | Cost/Use
PM | PMO | PM - Project Manager |  | 100% | $150.00/hr | 0
PCL | PMO | PM - Project Controls Lead |  | 100% | $140.00/hr | 0
SCH | PMO | PM - Scheduler |  | 100% | $120.00/hr | 0
CC | PMO | PM - Cost Controller |  | 100% | $120.00/hr | 0
DC | PMO | PM - Document Control |  | 100% | $55.00/hr | 0
CA | PMO | PM - Contracts/Admin |  | 100% | $85.00/hr | 0
EM | Engineering | ENG - Engineering Manager |  | 100% | $145.00/hr | 0
PE | Engineering | ENG - Process Engineer |  | 200% | $135.00/hr | 0
ME | Engineering | ENG - Mechanical Engineer |  | 200% | $135.00/hr | 0
CSE | Engineering | ENG - Civil/Structural Engineer |  | 150% | $135.00/hr | 0
EE | Engineering | ENG - Electrical Engineer |  | 150% | $135.00/hr | 0
ICE | Engineering | ENG - Instrument/Controls Engineer |  | 150% | $135.00/hr | 0
PLE | Engineering | ENG - Pipeline Engineer |  | 150% | $135.00/hr | 0
CAD | Engineering | ENG - CAD/Designer |  | 300% | $85.00/hr | 0
PL | Procurement | PROC - Procurement Lead |  | 100% | $120.00/hr | 0
BE | Procurement | PROC - Buyer/Expeditor |  | 200% | $85.00/hr | 0
QCI | Procurement | PROC - QA/QC Inspector |  | 150% | $90.00/hr | 0
RPL | Regulatory | REG - Permitting Lead |  | 100% | $115.00/hr | 0
LA | Regulatory | REG - Land Agent |  | 200% | $95.00/hr | 0
ENV | Regulatory | REG - Environmental Specialist |  | 100% | $105.00/hr | 0
CM | Construction | CON - Construction Manager |  | 100% | $145.00/hr | 0
HSE | Construction | CON - HSE Officer |  | 100% | $90.00/hr | 0
QC | Construction | CON - QA/QC Inspector |  | 150% | $90.00/hr | 0
SPC | Civil | CIV - Site Prep Crew |  | 300% | $120.00/hr | 0
EWC | Civil | CIV - Earthworks Crew |  | 400% | $125.00/hr | 0
UUC | Civil | CIV - Underground Utilities Crew |  | 300% | $130.00/hr | 0
CONC | Civil | CIV - Concrete Crew |  | 400% | $135.00/hr | 0
SEC | Structural | STR - Steel Erection Crew |  | 500% | $140.00/hr | 0
CRN | Structural | STR - Crane Operator |  | 200% | $125.00/hr | 0
RIG | Mechanical | MECH - Rigging Crew |  | 300% | $135.00/hr | 0
ESC | Mechanical | MECH - Equipment Setting Crew |  | 300% | $140.00/hr | 0
PF | Mechanical | MECH - Pipefitters Crew |  | 600% | $140.00/hr | 0
WLD | Mechanical | MECH - Welders Crew |  | 600% | $150.00/hr | 0
NDT | Mechanical | MECH - NDE/NDT Technician |  | 200% | $150.00/hr | 0
HT | Mechanical | MECH - Hydrotest Crew |  | 200% | $135.00/hr | 0
ELC | E&I | E&I - Electrical Crew |  | 500% | $145.00/hr | 0
INS | E&I | E&I - Instrument Crew |  | 400% | $145.00/hr | 0
CTC | E&I | E&I - Cable Tray Crew |  | 300% | $135.00/hr | 0
CPC | E&I | E&I - Cable Pull Crew |  | 300% | $135.00/hr | 0
TRM | E&I | E&I - Termination Crew |  | 300% | $145.00/hr | 0
CIT | E&I | E&I - Controls Integration Team |  | 200% | $160.00/hr | 0
PS | Pipeline | PIPE - Pipeline Superintendent |  | 100% | $140.00/hr | 0
ROW | Pipeline | PIPE - ROW Clearing Crew |  | 400% | $125.00/hr | 0
STRG | Pipeline | PIPE - Stringing Crew |  | 300% | $130.00/hr | 0
BND | Pipeline | PIPE - Bending Crew |  | 200% | $140.00/hr | 0
PW | Pipeline | PIPE - Welding Crew |  | 600% | $155.00/hr | 0
PNDT | Pipeline | PIPE - NDT Crew |  | 300% | $155.00/hr | 0
COAT | Pipeline | PIPE - Coating Crew |  | 300% | $135.00/hr | 0
LWR | Pipeline | PIPE - Lower-In Crew |  | 300% | $135.00/hr | 0
PHT | Pipeline | PIPE - Hydrotest Crew |  | 200% | $135.00/hr | 0
CL | Commissioning | COM - Commissioning Lead |  | 100% | $160.00/hr | 0
OPS | Commissioning | COM - Operators/Start-Up Team |  | 300% | $120.00/hr | 0
LCT | Commissioning | COM - Controls/Loop Check Team |  | 300% | $145.00/hr | 0
VR | Commissioning | COM - Vendor Rep (Compressor) |  | 100% | $220.00/hr | 0
TOT | Closeout | CLO - Turnover/As-Builts Team |  | 200% | $95.00/hr | 0
TC | Closeout | CLO - Training Coordinator |  | 100% | $90.00/hr | 0
CP | Major Equip |  | MAT - Compressor Package |  | 0 | 62000000
STL | Materials |  | MAT - Structural Steel Supply |  | 0 | 2500000
PIP | Materials |  | MAT - Piping Bulks Supply |  | 0 | 4000000
EIB | Materials |  | MAT - E&I Bulks Supply |  | 0 | 3500000
LNP | Pipeline Mat |  | MAT - Line Pipe Supply |  | 0 | 4500000
PVF | Pipeline Mat |  | MAT - Pipeline Valves/Fittings |  | 0 | 1200000
CRR | Equipment | EQ - Crane Rental |  | 100% | $0.00/hr | 3500
EXD | Equipment | EQ - Excavator/Dozer Rental |  | 100% | $0.00/hr | 2200
HTP | Equipment | EQ - Hydrotest Pumps Rental |  | 100% | $0.00/hr | 1200

## Predecessors (hidden)
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | PREDTASK__PROJWBS__wbs_full_name | TASK__PROJWBS__wbs_full_name | PREDTASK__task_name | TASK__task_name | lag_hr_cnt | PREDTASK__rsrc_id | TASK__rsrc_id | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag(h) | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Delete This Row
13 | 2 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.1 Project Milestones | PM-1000 Notice to Proceed | MS-9000 Project Kickoff | 0
54 | 3 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.1 Project Milestones | ENG-1430 Mech Package IFC Issued | MS-9010 IFC Issued – All Disciplines | 0
63 | 3 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.1 Project Milestones | ENG-1570 Structural IFC Issued | MS-9010 IFC Issued – All Disciplines | 0
72 | 3 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.1 Project Milestones | ENG-1670 Electrical IFC Issued | MS-9010 IFC Issued – All Disciplines | 0
80 | 3 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.1 Project Milestones | ENG-1760 Controls IFC Issued | MS-9010 IFC Issued – All Disciplines | 0
89 | 3 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.1 Project Milestones | ENG-1870 Pipeline IFC Issued | MS-9010 IFC Issued – All Disciplines | 0
110 | 4 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.1 Project Milestones | PRO-3090 Compressor Received | MS-9020 Compressor Delivered | 0
195 | 5 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.8 5.8 Tie-Ins | ABOG100.1 Project Milestones | CON-4840 Plant Mech Completion | MS-9030 Mech Completion – Plant | 0
220 | 6 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.7.4 6.4 Pipeline Testing | ABOG100.1 Project Milestones | PL-5340 Pipeline Mech Completion | MS-9040 Mech Completion – Pipeline | 0
229 | 7 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.1 Project Milestones | COM-6060 Pre-Comm Complete | MS-9050 Ready for Start-Up | 0
5 | 7 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.1 Project Milestones | MS-9030 Mech Completion – Plant | MS-9050 Ready for Start-Up | 0
6 | 7 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.1 Project Milestones | MS-9040 Mech Completion – Pipeline | MS-9050 Ready for Start-Up | 0
235 | 8 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.2 7.2 Start-Up | ABOG100.1 Project Milestones | COM-6140 First Gas | MS-9060 First Gas | 0
236 | 9 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.2 7.2 Start-Up | ABOG100.1 Project Milestones | COM-6150 Performance Test | MS-9070 Performance Test Complete | 0
9 | 10 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.1 Project Milestones | MS-9070 Performance Test Complete | MS-9080 Substantial Completion | 0
240 | 10 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.9 8.0 Closeout | ABOG100.1 Project Milestones | CLO-7010 As-Builts | MS-9080 Substantial Completion | 0
241 | 10 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.9 8.0 Closeout | ABOG100.1 Project Milestones | CLO-7020 O&M Manuals | MS-9080 Substantial Completion | 0
242 | 10 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.9 8.0 Closeout | ABOG100.1 Project Milestones | CLO-7030 Training | MS-9080 Substantial Completion | 0
239 | 11 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.9 8.0 Closeout | ABOG100.1 Project Milestones | CLO-7000 Punchlist Close | MS-9090 Final Completion | 0
13 | 14 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1000 Notice to Proceed | PM-1010 Controls Setup | 0
14 | 15 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1010 Controls Setup | PM-1020 Baseline Schedule Build | 0
14 | 16 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1010 Controls Setup | PM-1030 Baseline Cost Load | 0
15 | 17 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1020 Baseline Schedule Build | PM-1040 Baseline Approval | 0
16 | 17 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1030 Baseline Cost Load | PM-1040 Baseline Approval | 0
14 | 18 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1010 Controls Setup | PM-1060 Change Control Setup | 0
14 | 19 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1010 Controls Setup | PM-1070 Risk Register Setup | 0
14 | 20 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.2 1.0 Project Management & Controls | PM-1010 Controls Setup | PM-1080 Progress Measurement Plan | 0
13 | 23 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.3.1 2.1 Engineering Management | PM-1000 Notice to Proceed | ENG-1100 Engineering Kickoff | 0
23 | 24 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.1 2.1 Engineering Management | ABOG100.3.1 2.1 Engineering Management | ENG-1100 Engineering Kickoff | ENG-1110 Finalize Basis of Design | 0
24 | 25 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.1 2.1 Engineering Management | ABOG100.3.1 2.1 Engineering Management | ENG-1110 Finalize Basis of Design | ENG-1120 Design Criteria | 0
23 | 26 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.1 2.1 Engineering Management | ABOG100.3.1 2.1 Engineering Management | ENG-1100 Engineering Kickoff | ENG-1130 Model Setup | 0
47 | 27 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1360 Line List | ENG-1140 30% Design Review | 0
58 | 27 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1520 Grading Plan | ENG-1140 30% Design Review | 0
65 | 27 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1600 Load Study | ENG-1140 30% Design Review | 0
74 | 27 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.1 2.1 Engineering Management | ENG-1700 Instrument Index | ENG-1140 30% Design Review | 0
33 | 27 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1220 P&ID Development | ENG-1140 30% Design Review | 0
50 | 28 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1390 BIM Model 60% | ENG-1150 60% Design Review | 0
60 | 28 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1540 Steel Design | ENG-1150 60% Design Review | 0
71 | 28 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1660 Substation Upgrade | ENG-1150 60% Design Review | 0
87 | 28 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1850 Alignment Sheets Issued | ENG-1150 60% Design Review | 0
51 | 29 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1400 BIM Model 90% | ENG-1160 90% Design Review | 0
52 | 29 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1410 Isometrics Issued | ENG-1160 90% Design Review | 0
76 | 29 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.1 2.1 Engineering Management | ENG-1720 Loop Diagrams | ENG-1160 90% Design Review | 0
87 | 29 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.1 2.1 Engineering Management | ENG-1850 Alignment Sheets Issued | ENG-1160 90% Design Review | 0
24 | 31 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.1 2.1 Engineering Management | ABOG100.3.2 2.2 Process Engineering | ENG-1110 Finalize Basis of Design | ENG-1200 PFD Development | 0
31 | 32 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1200 PFD Development | ENG-1210 Heat & Material Balance | 0
32 | 33 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1210 Heat & Material Balance | ENG-1220 P&ID Development | 0
33 | 34 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1220 P&ID Development | ENG-1230 Control Philosophy | 0
33 | 35 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1220 P&ID Development | ENG-1240 Relief Review | 0
34 | 36 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1230 Control Philosophy | ENG-1250 Cause & Effect Draft | 0
33 | 37 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1220 P&ID Development | ENG-1260 HAZOP Prep | 0
37 | 38 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1260 HAZOP Prep | ENG-1270 HAZOP Session | 0
38 | 39 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.2 2.2 Process Engineering | ENG-1270 HAZOP Session | ENG-1280 HAZOP Closeout | 0
33 | 41 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1220 P&ID Development | ENG-1300 Equipment List | 0
41 | 42 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1300 Equipment List | ENG-1310 Compressor Datasheets | 0
41 | 43 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1300 Equipment List | ENG-1320 Separator Datasheets | 0
41 | 44 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1300 Equipment List | ENG-1330 Dehydration Datasheets | 0
41 | 45 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1300 Equipment List | ENG-1340 Cooler Datasheets | 0
47 | 46 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1360 Line List | ENG-1350 Valve List | 0
33 | 47 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1220 P&ID Development | ENG-1360 Line List | 0
47 | 48 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1360 Line List | ENG-1370 Piping Classes | 0
48 | 49 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1370 Piping Classes | ENG-1380 BIM Model 30% | 0
49 | 50 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1380 BIM Model 30% | ENG-1390 BIM Model 60% | 0
50 | 51 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1390 BIM Model 60% | ENG-1400 BIM Model 90% | 0
51 | 52 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1400 BIM Model 90% | ENG-1410 Isometrics Issued | 0
52 | 53 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1410 Isometrics Issued | ENG-1420 Pipe Support Design | 0
52 | 54 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1410 Isometrics Issued | ENG-1430 Mech Package IFC Issued | 0
53 | 54 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1420 Pipe Support Design | ENG-1430 Mech Package IFC Issued | 0
39 | 54 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.3 2.3 Mechanical Engineering | ENG-1280 HAZOP Closeout | ENG-1430 Mech Package IFC Issued | 0
23 | 56 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.1 2.1 Engineering Management | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1100 Engineering Kickoff | ENG-1500 Site Survey | 0
56 | 57 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1500 Site Survey | ENG-1510 Geotech Review | 0
57 | 58 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1510 Geotech Review | ENG-1520 Grading Plan | 0
57 | 59 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1510 Geotech Review | ENG-1530 Foundations Design | 0
59 | 60 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1530 Foundations Design | ENG-1540 Steel Design | 0
60 | 61 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1540 Steel Design | ENG-1550 Anchor Bolt Plans | 0
60 | 62 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1540 Steel Design | ENG-1560 Steel Connection Details | 0
61 | 63 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1550 Anchor Bolt Plans | ENG-1570 Structural IFC Issued | 0
62 | 63 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.4 2.4 Civil/Structural Engineering | ENG-1560 Steel Connection Details | ENG-1570 Structural IFC Issued | 0
41 | 65 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1300 Equipment List | ENG-1600 Load Study | 0
65 | 66 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1600 Load Study | ENG-1610 Single-Line Diagrams | 0
66 | 67 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1610 Single-Line Diagrams | ENG-1620 MCC Sizing | 0
67 | 68 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1620 MCC Sizing | ENG-1630 Cable Schedule | 0
58 | 69 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1520 Grading Plan | ENG-1640 Grounding Design | 0
33 | 70 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1220 P&ID Development | ENG-1650 Area Classification | 0
67 | 71 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1620 MCC Sizing | ENG-1660 Substation Upgrade | 0
68 | 72 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1630 Cable Schedule | ENG-1670 Electrical IFC Issued | 0
71 | 72 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1660 Substation Upgrade | ENG-1670 Electrical IFC Issued | 0
69 | 72 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1640 Grounding Design | ENG-1670 Electrical IFC Issued | 0
70 | 72 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.3.5 2.5 Electrical Engineering | ENG-1650 Area Classification | ENG-1670 Electrical IFC Issued | 0
33 | 74 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1220 P&ID Development | ENG-1700 Instrument Index | 0
74 | 75 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1700 Instrument Index | ENG-1710 IO List | 0
75 | 76 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1710 IO List | ENG-1720 Loop Diagrams | 0
34 | 77 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1230 Control Philosophy | ENG-1730 Control Narrative | 0
36 | 78 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.2 2.2 Process Engineering | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1250 Cause & Effect Draft | ENG-1740 Cause & Effect Final | 0
75 | 79 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1710 IO List | ENG-1750 DCS Architecture | 0
76 | 80 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1720 Loop Diagrams | ENG-1760 Controls IFC Issued | 0
78 | 80 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1740 Cause & Effect Final | ENG-1760 Controls IFC Issued | 0
79 | 80 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.3.6 2.6 Instrumentation & Controls | ENG-1750 DCS Architecture | ENG-1760 Controls IFC Issued | 0
23 | 82 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.1 2.1 Engineering Management | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1100 Engineering Kickoff | ENG-1800 Route Selection | 0
82 | 83 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1800 Route Selection | ENG-1810 Environmental Screening | 0
83 | 84 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1810 Environmental Screening | ENG-1820 ROW Support | 0
83 | 85 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1810 Environmental Screening | ENG-1830 Watercourse Design | 0
82 | 86 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1800 Route Selection | ENG-1840 Wall Thickness Calc | 0
86 | 87 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1840 Wall Thickness Calc | ENG-1850 Alignment Sheets Issued | 0
85 | 87 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1830 Watercourse Design | ENG-1850 Alignment Sheets Issued | 0
87 | 88 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1850 Alignment Sheets Issued | ENG-1860 Tie-In Details | 0
87 | 89 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1850 Alignment Sheets Issued | ENG-1870 Pipeline IFC Issued | 0
88 | 89 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.3.7 2.7 Pipeline Engineering | ENG-1860 Tie-In Details | ENG-1870 Pipeline IFC Issued | 0
13 | 91 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.2 1.0 Project Management & Controls | ABOG100.4 3.0 Permits / Regulatory / Land | PM-1000 Notice to Proceed | REG-2000 Permit Strategy | 0
91 | 92 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.4 3.0 Permits / Regulatory / Land | REG-2000 Permit Strategy | REG-2010 Submit Approvals | 0
89 | 92 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.4 3.0 Permits / Regulatory / Land | ENG-1870 Pipeline IFC Issued | REG-2010 Submit Approvals | 0
83 | 93 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.4 3.0 Permits / Regulatory / Land | ENG-1810 Environmental Screening | REG-2020 Mitigation Plan | 0
84 | 94 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.4 3.0 Permits / Regulatory / Land | ENG-1820 ROW Support | REG-2030 Land Access Agreements | 0
84 | 95 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.4 3.0 Permits / Regulatory / Land | ENG-1820 ROW Support | REG-2040 Indigenous Engagement | 0
94 | 96 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.4 3.0 Permits / Regulatory / Land | REG-2030 Land Access Agreements | REG-2050 ROW Secured | 0
95 | 96 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.4 3.0 Permits / Regulatory / Land | REG-2040 Indigenous Engagement | REG-2050 ROW Secured | 0
92 | 97 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.4 3.0 Permits / Regulatory / Land | REG-2010 Submit Approvals | REG-2060 Permits Approved | 0
93 | 97 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.4 3.0 Permits / Regulatory / Land | REG-2020 Mitigation Plan | REG-2060 Permits Approved | 0
42 | 100 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.5.1 4.1 Long-Lead Equipment | ENG-1310 Compressor Datasheets | PRO-3000 RFQ – Compressor | 0
100 | 101 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3000 RFQ – Compressor | PRO-3010 Tech Eval – Compressor | 0
101 | 102 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3010 Tech Eval – Compressor | PRO-3020 Comm Eval – Compressor | 0
102 | 103 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3020 Comm Eval – Compressor | PRO-3030 Compressor PO Award | 0
103 | 104 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3030 Compressor PO Award | PRO-3030 Compressor Shop Drawings | 0
104 | 105 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3030 Compressor Shop Drawings | PRO-3040 Vendor Review Cycle 1 | 0
105 | 106 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3040 Vendor Review Cycle 1 | PRO-3050 Vendor Review Cycle 2 | 0
106 | 107 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3050 Vendor Review Cycle 2 | PRO-3060 Compressor Fabrication | 0
107 | 108 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3060 Compressor Fabrication | PRO-3070 Compressor FAT | 0
108 | 109 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3070 Compressor FAT | PRO-3080 Ship Compressor | 0
109 | 110 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.1 4.1 Long-Lead Equipment | ABOG100.5.1 4.1 Long-Lead Equipment | PRO-3080 Ship Compressor | PRO-3090 Compressor Received | 0
60 | 112 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.4 2.4 Civil/Structural Engineering | ABOG100.5.2 4.2 Bulks & Materials | ENG-1540 Steel Design | PRO-3100 RFQ – Structural Steel | 0
112 | 113 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3100 RFQ – Structural Steel | PRO-3110 Steel Award | 0
113 | 114 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3110 Steel Award | PRO-3120 Steel Shop Drawings | 0
115 | 116 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3140 Steel Fabrication | PRO-3150 Deliver Steel | 0
48 | 117 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.3 2.3 Mechanical Engineering | ABOG100.5.2 4.2 Bulks & Materials | ENG-1370 Piping Classes | PRO-3160 RFQ – Piping Bulks | 0
117 | 118 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3160 RFQ – Piping Bulks | PRO-3170 Piping Bulks Award | 0
118 | 119 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3170 Piping Bulks Award | PRO-3180 Receive Piping Bulks | 0
68 | 120 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.5 2.5 Electrical Engineering | ABOG100.5.2 4.2 Bulks & Materials | ENG-1630 Cable Schedule | PRO-3190 RFQ – E&I Bulks | 0
74 | 120 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.6 2.6 Instrumentation & Controls | ABOG100.5.2 4.2 Bulks & Materials | ENG-1700 Instrument Index | PRO-3190 RFQ – E&I Bulks | 0
120 | 121 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3190 RFQ – E&I Bulks | PRO-3200 E&I Bulks Award | 0
121 | 122 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3200 E&I Bulks Award | PRO-3205 Electrical Shop Drawings | 0
122 | 123 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.5.2 4.2 Bulks & Materials | PRO-3205 Electrical Shop Drawings | PRO-3210 Receive E&I Bulks | 0
86 | 125 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.3.7 2.7 Pipeline Engineering | ABOG100.5.3 4.3 Pipeline Materials | ENG-1840 Wall Thickness Calc | PRO-3300 RFQ – Line Pipe | 0
125 | 126 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.3 4.3 Pipeline Materials | ABOG100.5.3 4.3 Pipeline Materials | PRO-3300 RFQ – Line Pipe | PRO-3310 Line Pipe Award | 0
126 | 127 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.3 4.3 Pipeline Materials | ABOG100.5.3 4.3 Pipeline Materials | PRO-3310 Line Pipe Award | PRO-3315 Line Pipe Mill Data / Coating Submittals | 0
127 | 128 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.3 4.3 Pipeline Materials | ABOG100.5.3 4.3 Pipeline Materials | PRO-3315 Line Pipe Mill Data / Coating Submittals | PRO-3320 Line Pipe Coating | 0
128 | 129 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.3 4.3 Pipeline Materials | ABOG100.5.3 4.3 Pipeline Materials | PRO-3320 Line Pipe Coating | PRO-3330 Deliver Line Pipe | 0
126 | 130 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.3 4.3 Pipeline Materials | ABOG100.5.3 4.3 Pipeline Materials | PRO-3310 Line Pipe Award | PRO-3340 Receive Pipeline Valves | 0
3 | 132 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.5.4 4.4 Subcontract Awards | MS-9010 IFC Issued – All Disciplines | PRO-3400 Tender Civil Contractor | 0
132 | 133 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.4 4.4 Subcontract Awards | ABOG100.5.4 4.4 Subcontract Awards | PRO-3400 Tender Civil Contractor | PRO-3410 Civil Contractor Award | 0
3 | 134 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.5.4 4.4 Subcontract Awards | MS-9010 IFC Issued – All Disciplines | PRO-3420 Tender Mechanical Contractor | 0
134 | 135 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.4 4.4 Subcontract Awards | ABOG100.5.4 4.4 Subcontract Awards | PRO-3420 Tender Mechanical Contractor | PRO-3430 Mechanical Contractor Award | 0
3 | 136 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.5.4 4.4 Subcontract Awards | MS-9010 IFC Issued – All Disciplines | PRO-3440 Tender E&I Contractor | 0
136 | 137 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.4 4.4 Subcontract Awards | ABOG100.5.4 4.4 Subcontract Awards | PRO-3440 Tender E&I Contractor | PRO-3450 E&I Contractor Award | 0
3 | 138 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.5.4 4.4 Subcontract Awards | MS-9010 IFC Issued – All Disciplines | PRO-3460 Tender Pipeline Contractor | 0
96 | 138 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.5.4 4.4 Subcontract Awards | REG-2050 ROW Secured | PRO-3460 Tender Pipeline Contractor | 0
138 | 139 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.4 4.4 Subcontract Awards | ABOG100.5.4 4.4 Subcontract Awards | PRO-3460 Tender Pipeline Contractor | PRO-3470 Pipeline Contractor Award | 0
133 | 142 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.4 4.4 Subcontract Awards | ABOG100.6.1 5.1 Site Prep | PRO-3410 Civil Contractor Award | CON-4000 Plant Mobilization | 0
142 | 143 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.1 5.1 Site Prep | ABOG100.6.1 5.1 Site Prep | CON-4000 Plant Mobilization | CON-4010 Temp Facilities Setup | 0
142 | 144 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.1 5.1 Site Prep | ABOG100.6.1 5.1 Site Prep | CON-4000 Plant Mobilization | CON-4020 Survey & Layout | 0
144 | 145 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.1 5.1 Site Prep | ABOG100.6.1 5.1 Site Prep | CON-4020 Survey & Layout | CON-4030 Clearing | 0
145 | 147 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.1 5.1 Site Prep | ABOG100.6.2 5.2 Civil & Foundations | CON-4030 Clearing | CON-4100 Earthworks | 0
147 | 148 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.2 5.2 Civil & Foundations | ABOG100.6.2 5.2 Civil & Foundations | CON-4100 Earthworks | CON-4110 Underground Utilities | 0
147 | 149 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.2 5.2 Civil & Foundations | ABOG100.6.2 5.2 Civil & Foundations | CON-4100 Earthworks | CON-4120 Form Foundations | 0
149 | 150 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.2 5.2 Civil & Foundations | ABOG100.6.2 5.2 Civil & Foundations | CON-4120 Form Foundations | CON-4130 Rebar Install | 0
150 | 151 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.2 5.2 Civil & Foundations | ABOG100.6.2 5.2 Civil & Foundations | CON-4130 Rebar Install | CON-4140 Pour Foundations | 0
151 | 152 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.2 5.2 Civil & Foundations | ABOG100.6.2 5.2 Civil & Foundations | CON-4140 Pour Foundations | CON-4150 Cure & Backfill | 0
152 | 154 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.2 5.2 Civil & Foundations | ABOG100.6.3 5.3 Structural Steel | CON-4150 Cure & Backfill | CON-4200 Erect Columns | 0
116 | 154 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.6.3 5.3 Structural Steel | PRO-3150 Deliver Steel | CON-4200 Erect Columns | 0
154 | 155 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.3 5.3 Structural Steel | CON-4200 Erect Columns | CON-4210 Erect Beams | 0
155 | 156 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.3 5.3 Structural Steel | CON-4210 Erect Beams | CON-4220 Install Grating | 0
155 | 157 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.3 5.3 Structural Steel | CON-4210 Erect Beams | CON-4230 Install Pipe Rack Steel | 0
4 | 159 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.6.4 5.4 Mechanical Installation | MS-9020 Compressor Delivered | CON-4300 Receive Equipment | 0
157 | 160 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.4 5.4 Mechanical Installation | CON-4230 Install Pipe Rack Steel | CON-4310 Set Vessels | 0
157 | 161 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.4 5.4 Mechanical Installation | CON-4230 Install Pipe Rack Steel | CON-4320 Set Exchangers | 0
157 | 162 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.4 5.4 Mechanical Installation | CON-4230 Install Pipe Rack Steel | CON-4330 Set Compressor | 0
4 | 162 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.6.4 5.4 Mechanical Installation | MS-9020 Compressor Delivered | CON-4330 Set Compressor | 0
162 | 163 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.4 5.4 Mechanical Installation | CON-4330 Set Compressor | CON-4340 Install Skid Piping | 0
119 | 163 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.6.4 5.4 Mechanical Installation | PRO-3180 Receive Piping Bulks | CON-4340 Install Skid Piping | 0
157 | 164 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.4 5.4 Mechanical Installation | CON-4230 Install Pipe Rack Steel | CON-4350 Install Spools – Area A | 0
119 | 164 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.6.4 5.4 Mechanical Installation | PRO-3180 Receive Piping Bulks | CON-4350 Install Spools – Area A | 0
157 | 165 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.4 5.4 Mechanical Installation | CON-4230 Install Pipe Rack Steel | CON-4360 Install Spools – Area B | 0
119 | 165 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.6.4 5.4 Mechanical Installation | PRO-3180 Receive Piping Bulks | CON-4360 Install Spools – Area B | 0
164 | 166 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.4 5.4 Mechanical Installation | CON-4350 Install Spools – Area A | CON-4370 Install Valves | 0
165 | 166 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.4 5.4 Mechanical Installation | CON-4360 Install Spools – Area B | CON-4370 Install Valves | 0
166 | 167 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.4 5.4 Mechanical Installation | CON-4370 Install Valves | CON-4380 NDE / PWHT | 0
167 | 168 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.4 5.4 Mechanical Installation | CON-4380 NDE / PWHT | CON-4390 Piping Hydrotest | 0
168 | 169 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.4 5.4 Mechanical Installation | CON-4390 Piping Hydrotest | CON-4400 Drying & Reinstatement | 0
147 | 171 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.2 5.2 Civil & Foundations | ABOG100.6.5 5.5 Electrical Installation | CON-4100 Earthworks | CON-4500 Install Ground Grid | 0
157 | 172 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.5 5.5 Electrical Installation | CON-4230 Install Pipe Rack Steel | CON-4510 Install Cable Tray | 0
172 | 173 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.5 5.5 Electrical Installation | CON-4510 Install Cable Tray | CON-4520 Pull Power Cables | 0
123 | 173 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.6.5 5.5 Electrical Installation | PRO-3210 Receive E&I Bulks | CON-4520 Pull Power Cables | 0
172 | 174 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.5 5.5 Electrical Installation | CON-4510 Install Cable Tray | CON-4530 Pull Control Cables | 0
123 | 174 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.6.5 5.5 Electrical Installation | PRO-3210 Receive E&I Bulks | CON-4530 Pull Control Cables | 0
173 | 175 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.5 5.5 Electrical Installation | CON-4520 Pull Power Cables | CON-4540 MCC Terminations | 0
174 | 176 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.5 5.5 Electrical Installation | CON-4530 Pull Control Cables | CON-4550 Field Terminations | 0
173 | 177 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.5 5.5 Electrical Installation | CON-4520 Pull Power Cables | CON-4560 Lighting & Heat Trace | 0
175 | 178 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.5 5.5 Electrical Installation | CON-4540 MCC Terminations | CON-4570 Energize Substation | 0
177 | 178 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.5 5.5 Electrical Installation | CON-4560 Lighting & Heat Trace | CON-4570 Energize Substation | 0
164 | 180 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.6 5.6 I&C Installation | CON-4350 Install Spools – Area A | CON-4600 Install Instruments | 0
165 | 180 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.6 5.6 I&C Installation | CON-4360 Install Spools – Area B | CON-4600 Install Instruments | 0
123 | 180 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.2 4.2 Bulks & Materials | ABOG100.6.6 5.6 I&C Installation | PRO-3210 Receive E&I Bulks | CON-4600 Install Instruments | 0
166 | 181 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.6 5.6 I&C Installation | CON-4370 Install Valves | CON-4610 Install Control Valves | 0
157 | 182 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.3 5.3 Structural Steel | ABOG100.6.6 5.6 I&C Installation | CON-4230 Install Pipe Rack Steel | CON-4620 Install Analyzers | 0
172 | 183 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.6 5.6 I&C Installation | CON-4510 Install Cable Tray | CON-4630 Install Junction Boxes | 0
176 | 184 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.6 5.6 I&C Installation | CON-4550 Field Terminations | CON-4640 Loop Checks | 0
180 | 184 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.6.6 5.6 I&C Installation | ABOG100.6.6 5.6 I&C Installation | CON-4600 Install Instruments | CON-4640 Loop Checks | 0
178 | 184 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.6.6 5.6 I&C Installation | CON-4570 Energize Substation | CON-4640 Loop Checks | 0
184 | 185 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.6 5.6 I&C Installation | ABOG100.6.6 5.6 I&C Installation | CON-4640 Loop Checks | CON-4650 Controls Testing | 0
164 | 187 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.7 5.7 Insulation & Paint | CON-4350 Install Spools – Area A | CON-4700 Paint Touch-Up | 0
165 | 187 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.7 5.7 Insulation & Paint | CON-4360 Install Spools – Area B | CON-4700 Paint Touch-Up | 0
168 | 188 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.7 5.7 Insulation & Paint | CON-4390 Piping Hydrotest | CON-4710 Insulation Install | 0
188 | 189 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.7 5.7 Insulation & Paint | ABOG100.6.7 5.7 Insulation & Paint | CON-4710 Insulation Install | CON-4720 Tagging & Labels | 0
169 | 191 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.8 5.8 Tie-Ins | CON-4400 Drying & Reinstatement | CON-4800 Shutdown Planning | 0
163 | 192 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.8 5.8 Tie-Ins | CON-4340 Install Skid Piping | CON-4810 Prefab Complete | 0
192 | 193 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.6.8 5.8 Tie-Ins | ABOG100.6.8 5.8 Tie-Ins | CON-4810 Prefab Complete | CON-4820 Execute Tie-Ins | 0
191 | 193 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.8 5.8 Tie-Ins | ABOG100.6.8 5.8 Tie-Ins | CON-4800 Shutdown Planning | CON-4820 Execute Tie-Ins | 0
193 | 194 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.8 5.8 Tie-Ins | ABOG100.6.8 5.8 Tie-Ins | CON-4820 Execute Tie-Ins | CON-4830 Tie-Ins Complete | 0
169 | 195 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.6.8 5.8 Tie-Ins | CON-4400 Drying & Reinstatement | CON-4840 Plant Mech Completion | 0
185 | 195 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.6 5.6 I&C Installation | ABOG100.6.8 5.8 Tie-Ins | CON-4650 Controls Testing | CON-4840 Plant Mech Completion | 0
194 | 195 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.8 5.8 Tie-Ins | ABOG100.6.8 5.8 Tie-Ins | CON-4830 Tie-Ins Complete | CON-4840 Plant Mech Completion | 0
189 | 195 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.7 5.7 Insulation & Paint | ABOG100.6.8 5.8 Tie-Ins | CON-4720 Tagging & Labels | CON-4840 Plant Mech Completion | 0
139 | 198 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.4 4.4 Subcontract Awards | ABOG100.7.1 6.1 ROW Prep | PRO-3470 Pipeline Contractor Award | PL-5000 Pipeline Mobilization | 0
96 | 198 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.7.1 6.1 ROW Prep | REG-2050 ROW Secured | PL-5000 Pipeline Mobilization | 0
97 | 198 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.4 3.0 Permits / Regulatory / Land | ABOG100.7.1 6.1 ROW Prep | REG-2060 Permits Approved | PL-5000 Pipeline Mobilization | 0
198 | 199 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.1 6.1 ROW Prep | ABOG100.7.1 6.1 ROW Prep | PL-5000 Pipeline Mobilization | PL-5010 Survey & Staking | 0
199 | 200 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.1 6.1 ROW Prep | ABOG100.7.1 6.1 ROW Prep | PL-5010 Survey & Staking | PL-5020 ROW Clearing | 0
200 | 201 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.1 6.1 ROW Prep | ABOG100.7.1 6.1 ROW Prep | PL-5020 ROW Clearing | PL-5030 Access Improvements | 0
201 | 203 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.1 6.1 ROW Prep | ABOG100.7.2 6.2 Mainline Construction | PL-5030 Access Improvements | PL-5100 Pipe Stringing | 0
129 | 203 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.5.3 4.3 Pipeline Materials | ABOG100.7.2 6.2 Mainline Construction | PRO-3330 Deliver Line Pipe | PL-5100 Pipe Stringing | 0
203 | 204 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.2 6.2 Mainline Construction | PL-5100 Pipe Stringing | PL-5110 Pipe Bending | 0
204 | 205 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.2 6.2 Mainline Construction | PL-5110 Pipe Bending | PL-5120 Mainline Welding | 0
205 | 206 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.2 6.2 Mainline Construction | PL-5120 Mainline Welding | PL-5130 Mainline NDT | 0
206 | 207 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.2 6.2 Mainline Construction | PL-5130 Mainline NDT | PL-5140 Field Joint Coating | 0
207 | 208 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.2 6.2 Mainline Construction | PL-5140 Field Joint Coating | PL-5150 Lower-In | 0
208 | 209 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.2 6.2 Mainline Construction | PL-5150 Lower-In | PL-5160 Backfill | 0
209 | 210 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.2 6.2 Mainline Construction | PL-5160 Backfill | PL-5170 Install Valves | 0
130 | 210 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.5.3 4.3 Pipeline Materials | ABOG100.7.2 6.2 Mainline Construction | PRO-3340 Receive Pipeline Valves | PL-5170 Install Valves | 0
201 | 212 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.1 6.1 ROW Prep | ABOG100.7.3 6.3 Crossings | PL-5030 Access Improvements | PL-5200 Watercourse Crossing | 0
201 | 213 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.1 6.1 ROW Prep | ABOG100.7.3 6.3 Crossings | PL-5030 Access Improvements | PL-5210 Road Crossing | 0
205 | 214 | FS | Completed | Completed | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.3 6.3 Crossings | PL-5120 Mainline Welding | PL-5220 Tie-In Spools Fab | 0
210 | 216 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.7.2 6.2 Mainline Construction | ABOG100.7.4 6.4 Pipeline Testing | PL-5170 Install Valves | PL-5300 Hydrotest Prep | 0
212 | 216 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.7.3 6.3 Crossings | ABOG100.7.4 6.4 Pipeline Testing | PL-5200 Watercourse Crossing | PL-5300 Hydrotest Prep | 0
213 | 216 | FS | Completed | Not Started | ABOG100 | ABOG100 | ABOG100.7.3 6.3 Crossings | ABOG100.7.4 6.4 Pipeline Testing | PL-5210 Road Crossing | PL-5300 Hydrotest Prep | 0
216 | 217 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.7.4 6.4 Pipeline Testing | ABOG100.7.4 6.4 Pipeline Testing | PL-5300 Hydrotest Prep | PL-5310 Hydrotest | 0
217 | 218 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.7.4 6.4 Pipeline Testing | ABOG100.7.4 6.4 Pipeline Testing | PL-5310 Hydrotest | PL-5320 Dewater & Purge | 0
218 | 219 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.7.4 6.4 Pipeline Testing | ABOG100.7.4 6.4 Pipeline Testing | PL-5320 Dewater & Purge | PL-5330 Final Tie-Ins | 0
219 | 220 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.7.4 6.4 Pipeline Testing | ABOG100.7.4 6.4 Pipeline Testing | PL-5330 Final Tie-Ins | PL-5340 Pipeline Mech Completion | 0
5 | 223 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.8.1 7.1 Pre-Commissioning | MS-9030 Mech Completion – Plant | COM-6000 Walkdowns | 0
6 | 223 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.8.1 7.1 Pre-Commissioning | MS-9040 Mech Completion – Pipeline | COM-6000 Walkdowns | 0
169 | 224 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.4 5.4 Mechanical Installation | ABOG100.8.1 7.1 Pre-Commissioning | CON-4400 Drying & Reinstatement | COM-6010 Flushing | 0
178 | 225 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.8.1 7.1 Pre-Commissioning | CON-4570 Energize Substation | COM-6020 Utilities Commissioning | 0
178 | 226 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.5 5.5 Electrical Installation | ABOG100.8.1 7.1 Pre-Commissioning | CON-4570 Energize Substation | COM-6030 Early Energization | 0
185 | 227 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.6.6 5.6 I&C Installation | ABOG100.8.1 7.1 Pre-Commissioning | CON-4650 Controls Testing | COM-6040 Controls Testing | 0
226 | 227 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.8.1 7.1 Pre-Commissioning | COM-6030 Early Energization | COM-6040 Controls Testing | 0
227 | 228 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.8.1 7.1 Pre-Commissioning | COM-6040 Controls Testing | COM-6050 Cause & Effect Testing | 0
223 | 229 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.8.1 7.1 Pre-Commissioning | COM-6000 Walkdowns | COM-6060 Pre-Comm Complete | 0
228 | 229 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.8.1 7.1 Pre-Commissioning | COM-6050 Cause & Effect Testing | COM-6060 Pre-Comm Complete | 0
224 | 229 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.8.1 7.1 Pre-Commissioning | COM-6010 Flushing | COM-6060 Pre-Comm Complete | 0
225 | 229 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.8.1 7.1 Pre-Commissioning | COM-6020 Utilities Commissioning | COM-6060 Pre-Comm Complete | 0
7 | 231 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.8.2 7.2 Start-Up | MS-9050 Ready for Start-Up | COM-6100 Introduce Gas | 0
231 | 232 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.2 7.2 Start-Up | ABOG100.8.2 7.2 Start-Up | COM-6100 Introduce Gas | COM-6110 Start Compressor | 0
232 | 233 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.2 7.2 Start-Up | ABOG100.8.2 7.2 Start-Up | COM-6110 Start Compressor | COM-6120 Ramp to Stable Ops | 0
229 | 234 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.1 7.1 Pre-Commissioning | ABOG100.8.2 7.2 Start-Up | COM-6060 Pre-Comm Complete | COM-6130 Ready for Start-Up | 0
233 | 235 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.2 7.2 Start-Up | ABOG100.8.2 7.2 Start-Up | COM-6120 Ramp to Stable Ops | COM-6140 First Gas | 0
235 | 236 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.2 7.2 Start-Up | ABOG100.8.2 7.2 Start-Up | COM-6140 First Gas | COM-6150 Performance Test | 0
236 | 237 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.8.2 7.2 Start-Up | ABOG100.8.2 7.2 Start-Up | COM-6150 Performance Test | COM-6160 Performance Test Passed | 0
10 | 239 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.9 8.0 Closeout | MS-9080 Substantial Completion | CLO-7000 Punchlist Close | 0
9 | 240 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.9 8.0 Closeout | MS-9070 Performance Test Complete | CLO-7010 As-Builts | 0
9 | 241 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.9 8.0 Closeout | MS-9070 Performance Test Complete | CLO-7020 O&M Manuals | 0
9 | 242 | FS | Not Started | Not Started | ABOG100 | ABOG100 | ABOG100.1 Project Milestones | ABOG100.9 8.0 Closeout | MS-9070 Performance Test Complete | CLO-7030 Training | 0